## TaskMap
TaskID	Name	Link	Overall Status
N_001	CSL Language :: Concat & Replication	N_001	91.88

N_002	CSL Language :: Parameters	N_002	75.33
N_003	CSL Language :: Prefix & Suffix	N_003	78.33
N_004	CSL Language :: do_not_gen_cpp()	N_004	90.91
N_005	CSL Language :: gen_unique_rtl_modules()	N_005	85
N_006	CSL Language :: set_clock()	N_006	63.33
N_007	CSL Language :: register_ios()	N_007	44
N_008	CSL Autorouter :: connect() method	N_008	81.71
N_009	CSLOM implementation support	N_009	90
N_010	CSLOM training class	N_010	30
N_011	Autoruter functionality class	N_011	50
N_012	SystemC codegen	N_012	0
N_013	VHDL Code generator	N_013	37.5
N_014	Distributed regression	N_014	0
N_015	CSIM functionality	N_015	50
N_016	Coverage tool evaluation	N_016	100
N_017	CSL Language :: Support for X and Z in numbers	N_017	40
N_018	Memory Map specification	N_018	0
N_019	ISA specification	N_019	0
N_020	Auto CSL generation	N_020	0
N_021	Marked up documents	N_021	75
N_022	iverilog install	N_022	100

## N_001
No	Task:	CSL Language :: Concat & Replication			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			MH	05/12/2008	05/17/2008		100
		Examples			MH	05/07/2008	05/10/2008		100
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/06/2008		100
			Treewalker		AB	05/05/2008	05/06/2008		100
			CSLOM CMD		MP	05/08/2008	05/08/2008		80
			CSLOM		OS	05/07/2008	05/08/2008		100
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/05/2008	05/10/2008		100
			Adapter		MP	05/05/2008	05/08/2008		90
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser		N/A				100
			Treewalker		N/A				100
			CDOM		N/A				100
			CDOM checker		N/A				100
			CDOM Verilog gen		AB				100
3	Testing	Specifications			MH	05/05/2008	05/07/2008		100
		Generated tests			MH	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden		AB				0
			new						N/A
	Overall status								91.88

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## 'file:///home/cristi/svn-fpl/misc/project_management/users/MonicaH_TL.ods'#Sheet1
Owner:	Monica Helgiu
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	Documentation :: Spec	100				Fix documentation	Med
CSL Language :: Concat & Replication	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	High
CSL Language :: Concat & Replication	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High
CSL Language :: Concat & Replication	Testing :: Generated	100				Provide generated tests for the current task EDIT: updated with all concat tests. Please update your status.	High
CSL Autorouter :: connect()	Documentation :: Examples	100				Write in a temporary doc connect spec provided by DP	High
CSL Language :: do_not_gen_cpp()	Documentation :: Spec	100				Fix documentation	Med
CSL Language :: do_not_gen_cpp()	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	Med
CSL Language :: X and Z values spec	Documentation :: Specs	80				Provide specification for numbers with X and Z (use the verilog spec)	High+
CSL Autrouter :: connect()	Documentation :: Specs	80				Fix the presentation for connect methods and current examples	High+
CSL Language :: Parameters	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	Low
CSL Language :: Prefix & Suffix	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	High
CSL Language :: gen_unique_rtl_modules()	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	High
CSL Language :: set_clock()	Documentation :: Examples	80				Provide CSL and Verilog examples for documentation	High
CSL Language :: register_ios()	Documentation :: Examples	80				Provide CSL and Verilog examples for documentation	High
CSL Autrouter :: connect()	Documentation :: Specs	80				Update connect methods naming (connect_by_name + connect_units)	High+
Docs :: CSL Language	Documentation :: Spec	90				Add Derek's markups to document	High++

## 'file:///home/cristi/svn-fpl/misc/project_management/users/AnamariaH_TL.ods'#Sheet1
The link could not be updated.
File:	file:///home/cristi/svn-fpl/misc/project_management/users/AnamariaH_TL.ods
Sheet:	Sheet1

## 'file:///home/cristi/svn-fpl/misc/project_management/users/OctavS_TL.ods'#Sheet1
Owner:	Octavian Stolnicu
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: Lexer & Parser	100				Add support for concat and replication	High++
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM	100				Review concat and replication implementation	High++
CSL Language :: Prefix & Suffix	SW :: CSL :: Lexer & Parser	100				Add support for prefix & suffix	High
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM	100				Add support for prefix & suffix	High
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Lexer & Parser	100				Add support for do_not_gen_cpp()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM	100				Add support for do_not_gen_cpp()	Med
CSL Language :: Parameters	SW :: CSL :: Lexer & Parser	100				Add support for parameters	High+
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: Lexer & Parser	100				Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: Lexer & Parser	100				Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: Lexer & Parser	100				Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	0				Attend BZ's CSLOM training classes	High++
CSL Language :: set_clock()	SW :: CSL :: CSLOM	0			Documentation?	Add support for set_clock()	High
Support :: Distributed regression	SW :: Support	0				Please test and provide functionality for the distributed regression. The script path is: trunk/scripts/ssh_dist_regress.pl	High
CSL Autorouter :: connect() method	SW :: CSL :: Lexer & Parser	90				Add support for all connect methods as described in auto router document (Current connect variants sub-chapter: pages 14-16)	High++
CSL Language :: register_ios()	SW :: CSL :: CSLOM	0				Add support for register_ios()	High
CSL Language :: Parameters	SW :: CSL :: CSLOM	50				Add support for parameters (integration with other CSLOm classes)	High++

## 'file:///home/cristi/svn-fpl/misc/project_management/users/AndreiB_TL.ods'#Sheet1
Owner:	Andrei Branzila
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: Treewalker	100				Add support for concat and replication	High++
CSL Language :: Concat & Replication	Testing :: Regression :: golden	0				Add tests from new to golden after all components comply	Low
CSL Language :: Parameters	SW :: CSL :: Treewalker	90				Add support for parameters	High
CSL Language :: Prefix & Suffix	SW :: CSL :: Treewalker	100				Add support for prefix & suffix	High
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: Treewalker	100				Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: Treewalker	100				Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: Treewalker	0				Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	50				Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0				Attend BZ's autorouter functionality presentation	High++
Memory Map specification	Documentation :: Spec	0				Provide specification for memory map with CGH	High++
ISA specification	Documentation :: Spec	0				Revise/Fix/Rewrite specification for ISA with CGH (check consistency between SW implementation and current documentation)	High++
CSL Autorouter :: connect() method	SW :: CSL :: Treewalker	100				Add support for all connect methods as described in auto router document (Current connect variants sub-chapter: pages 14-16)	High++
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Treewalker	100				Add support for do_not_gen_cpp()	High

## 'file:///home/cristi/svn-fpl/misc/project_management/users/MihaelaP_TL.ods'#Sheet1
Owner:	Mihaela Plaesu
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM_cmd	80				Add support for concat and replication	High++
CSL Language :: Concat & Replication	SW :: CSL :: Adapter	90				Add support for concat and replication	High++	Needs some testing
CSL Language :: Parameters	SW :: CSL :: CSLOM_cmd	0			CSLOm support needed	Add support for parameters	High+
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM_cmd	90			CSLOm support needed	Add support for prefix & suffix	High
CSL Language :: Prefix & Suffix	SW :: CSL :: Adapter	30				Add support for prefix & suffix	High
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM_cmd	100			CSLOm support needed	Add support for do_not_gen_cpp()	High
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM_cmd	100			CSLOm support needed	Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: CSLOM_cmd	80			CSLOm support needed	Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: CSLOM_cmd	50			CSLOm/TW support needed	Add support for register_ios()	High
CSL Language :: register_ios()	SW :: CSL :: Adapter	0				Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	100				Attend BZ's CSLOM training classes	High++

## 'file:///home/cristi/svn-fpl/misc/project_management/users/AndreiS_TL.ods'#Sheet1
Owner:	Andrei Susnea
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM check	100			CSLOM-	Add support for concat and replication	High++	Also added getWidth for concat and replication in CSLOM | 80% because it needs testing
CSL Language :: Parameters	SW :: CSL :: CSLOM check	0			CSLOM-	Add support for parameters	High+
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM check	0			CSLOM-	Add support for prefix & suffix	High
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM check	100			CSLOM-	Add support for do_not_gen_cpp()	High	N/A
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM check	100			CSLOM-	Add support for do_not_gen_cpp()	High	N/A
CSL Language :: set_clock()	SW :: CSL :: CSLOM check	0			CSLOM-	Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: CSLOM check	0			CSLOM-	Add support for set_clock()	High
CSLOM training class	SW :: CSL :: CSLOM	100				Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0				Attend BZ's autorouter functionality presentation	High++
support for X and Z in numbers	SW :: CSL :: CSLOM	0				Add support numbers with X and Z bit values. The spec should be the Verilog standard and MH will add this to CSL Language document	High++

## 'file:///home/cristi/svn-fpl/misc/project_management/users/PetronelaE_TL.ods'#Sheet1
Owner:	Petronela Ezaru
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Parameters	Testing :: Generated	100				Provide generated tests for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Generated	20				Provide generated tests for the current task	High++
SystemC codegen	SW :: SystemC :: generator	0				Read SystemC documentation and understand CSL vs SystemC implementations of interconnect	High
SW :: SystemC :: translate Verilog modules	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog port/signal declarations	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog module instances	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog formal to actual mappings	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog module parameters	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog initial blocks	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog always blocks	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog conditionals (if else, case)	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog for loops	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog operators	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog expressions	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog statements	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High

## N_002
No	Task:	CSL Language :: Parameters			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			OB	06/01/2008	06/30/2008		90
		Examples			MH	06/01/2008	06/30/2008		100
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS				100
			Treewalker		AB	05/05/2008	05/08/2008		90
			CSLOM CMD		MP	05/08/2008	05/08/2008		0
			CSLOM		OS	05/05/2008	05/08/2008		50
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/05/2008	05/10/2008		0
			Adapter		TH	05/05/2008	05/08/2008		0
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser		N/A				100
			Treewalker		N/A				100
			CDOM		N/A				100
			CDOM checker		N/A				100
			CDOM Verilog gen		AB				100
3	Testing	Specifications			PE	05/05/2008	05/10/2008		100
		Generated tests			PE	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								75.33

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_003
No	Task:	CSL Language :: Prefix & Suffix			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			OB	06/01/2008	06/30/2008		50
		Examples			MH,CGH	06/01/2008	06/30/2008		85
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/06/2008		100
			Treewalker		AB	05/05/2008	05/06/2008		100
			CSLOM CMD		MP	05/08/2008	05/08/2008		90
			CSLOM		OS	05/08/2008	05/10/2008		100
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/05/2008	05/10/2008		0
			Adapter		MP	05/12/2008	05/14/2008		30
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser		N/A				100
			Treewalker		N/A				100
			CDOM		N/A				100
			CDOM checker		N/A				100
			CDOM Verilog gen		AB				100
3	Testing	Specifications			PE	05/05/2008	05/10/2008		100
		Generated tests			PE	05/05/2008	05/10/2008		20
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								78.33

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## 'file:///home/cristi/svn-fpl/misc/project_management/users/CostelC_TL.ods'#Sheet1
The link could not be updated.
File:	file:///home/cristi/svn-fpl/misc/project_management/users/CostelC_TL.ods
Sheet:	Sheet1

## 'file:///home/cristi/svn-fpl/misc/project_management/users/EugenC_TL.ods'#Sheet1
Owner:	Eugen Croitoru
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	SW :: CSL :: CSLOM	50				Add support for parameters	High++	Reassigned to OS
CSLOM training class	SW :: CSL :: CSLOM	0				Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0				Attend BZ's autorouter functionality presentation	High++

## 'file:///home/cristi/svn-fpl/misc/project_management/users/TiberiuH_TL.ods'#Sheet1
Owner:	Tiberiu Haret
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	SW :: CSL :: Adapter	0			CSLOM	Add support for parameters	High
CSL Language :: do_not_gen_cpp()	SW :: Main :: CLI	0			Specs	Add support for do_not_gen_cpp()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Adapter	100				Add support for do_not_gen_cpp()	High
CSL Interconnect :: gen_unique_rtl_module()	SW :: CSL :: Adapter	100				Add support for gen_unique_rtl_module()	High
CSLOM training class	SW :: CSL :: CSLOM	100				Attend BZ's CSLOM training classes	High++
CSL Interconnect :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM	50			Specs	Add support for gen_unique_rtl_modules()	High+
SW :: VHDL :: translate Verilog modules to entity and architecture	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High	still lots to learn about both Verilog and VHDL, so it's going to take me some time to implement this
SW :: VHDL :: translate Verilog port/signal declarations	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog module instances	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog formal to actual mappings	SW :: CDOM :: VHDL code generator	75	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog module parameters	SW :: CDOM :: VHDL code generator	75	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog initial blocks	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog always blocks	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog conditionals (if else, case)	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog for loops	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog operators	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog expressions	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog statements	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High

## N_004
No	Task:	CSL Language :: do_not_gen_cpp()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			MH	05/12/2008	05/17/2008		100
		Examples			MH	05/05/2008	05/10/2008		100
2	Software development	Main + CLI + GUI			TH				0		requires cli specs
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS				100
			Treewalker		AB				100
			CSLOM CMD		MP	05/14/2008	05/15/2008		100
			CSLOM		OS	05/12/2008	05/14/2008		100
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		100
			Adapter		TH	05/14/2008	05/15/2008		100
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/05/2008	05/10/2008		100
		Generated tests			OB	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								90.91

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_005
No	Task:	CSL Language :: gen_unique_rtl_modules()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			OB	06/01/2008	06/30/2008		50
		Examples			MH,CGH	06/01/2008	06/30/2008		50
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS				100
			Treewalker		AB				100
			CSLOM CMD		MP	05/14/2008	05/15/2008		100
			CSLOM		TH	05/14/2008	05/16/2008		50		vhdl codegen is a priority
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		100
			Adapter		TH	05/14/2008	05/15/2008		100
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/05/2008	05/10/2008		100
		Generated tests			OB	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								85

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_006
No	Task:	CSL Language :: set_clock()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			OB	06/01/2008	06/30/2008		50
		Examples			MH,CGH	06/01/2008	06/30/2008		40
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/09/2008		100
			Treewalker		AB	05/05/2008	05/09/2008		100
			CSLOM CMD		MP	05/14/2008	05/15/2008		80
			CSLOM		OS	05/14/2008	05/16/2008		0		in progress
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		0
			Adapter						N/A
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/26/2008	05/31/2008		100
		Generated tests			OB	05/26/2008	05/31/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								63.33

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_007
No	Task:	CSL Language :: register_ios()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			OB	06/01/2008	06/30/2008		50
		Examples			MH,CGH	06/01/2008	06/30/2008		40
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/09/2008		100
			Treewalker		AB	05/05/2008	05/09/2008		0
			CSLOM CMD		MP	05/14/2008	05/15/2008		50
			CSLOM		OS	06/01/2008	06/14/2008		0		depends on set_clock()
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		0
			Adapter		MP	05/14/2008	05/16/2008		0
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/26/2008	05/31/2008		100
		Generated tests			OB	05/26/2008	05/31/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								44

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_008
No	Task:	CSL Autorouter :: connect() method			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			OB,BZ,MH,CGH	05/05/2008	05/08/2008		82
		Examples			MH	05/08/2008	05/16/2008		100
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/22/2008	05/23/2008		90
			Treewalker		AB	05/23/2008	05/23/2008		100
			CSLOM CMD						N/A
			CSLOM						N/A
			Instance Tree + autorouter		BZ	05/08/2008	05/14/2008		70
			CSLOM Design Checker						N/A
			Adapter						N/A
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/12/2008	05/17/2008		70
		Generated tests			OB	05/12/2008	05/17/2008		60
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								81.71

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## 'file:///home/cristi/svn-fpl/misc/project_management/users/BogdanZ_TL.ods'#Sheet1
Owner:	Bogdan Zamfir
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM	100				Implement concat and replication + train OS/EC	High++	Has been implemented in cslom a long time ago
CSL Autorouter :: connect()	Documentation :: Spec	100				Detail current autorouter functionality to CGH	High++	Emails have been sent a long time ago.
CSL Autorouter :: connect()	SW :: CSL :: Autorouter	70	06/05/2008	06/12/2008		Provide autorouter functionality as in the spec document	High++	In progress, added new f2a_name and prefix without errors
CSLOM implementation support	SW :: CSL :: CSLOM	90				Provide support to OS/EC/TH/AS to implement their CSLOM related tasks	High++	I am waiting for questions and problems
CSLOM training class	SW :: CSL :: CSLOM	90				CSLOM training classes for the following employees: EC, OS, MP, AS, TH, AB (about 1-2 hours/day when at least 80% of the attendees are present at the office)	High++	Held the class, explained about everything i could, I'm waiting for questions
Autoruter functionality class	SW :: CSL :: Autorouter	0			AS, EC	Hold autorouter functionality presentation for the following employees: AS, EC, AB (about 1 hour/day when at least 60% of the attendees are present at the office)	High++	they have exams and school projects
Coverage tool evaluation	SW :: Support	100	06/02/2008	06/03/2008		Evaluate Bullseye coverage tool	High++	Bad report system, no improvement next to lcov
CSIM functionality	SW :: CSL :: CSIM	50	06/03/2008	06/05/2008		Need solutions and implementations for: single action compile, generated values difference between CSIM and Modelsim (due to flip flop propagation issue) talk to AB/OS for examples, load feature to load stimulus vectors from a file	High++	Implemeted execute order in simulator and support in shell, Still need implementation of CLI for csim binary

## 'file:///home/cristi/svn-fpl/misc/project_management/users/CristianH_TL.ods'#Sheet1
Owner:	Cristian Haba
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Autorouter :: connect()	Documentation :: Spec	50				Review and note in a temporary doc current autorouter functionality (provided by BZ)	High++
CSL Language :: Prefix & Suffix	Documentation :: Examples	70				Provide CSL and Verilog examples for documentation	High
CSL Language :: gen_unique_rtl_modules()	Documentation :: Examples	0				Provide CSL and Verilog examples for documentation	High
CSL Language :: set_clock()	Documentation :: Examples	0				Provide CSL and Verilog examples for documentation	High
CSL Language :: register_ios()	Documentation :: Examples	0				Provide CSL and Verilog examples for documentation	High
Memory Map specification	Documentation :: Spec	0				Provide specification for memory map with AB	High++
ISA specification	Documentation :: Spec	0				Revise/Fix/Rewrite specification for ISA with CGH (check consistency between SW implementation and current documentation)	High++

## 'file:///home/cristi/svn-fpl/misc/project_management/users/OanaB_TL.ods'#Sheet1
Owner:	Oana Botez
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Autorouter :: connect()	Documentation :: Spec	100				Outline current functionality in a temporary doc for each method from the autorouter doc	High++
CSL Language :: do_not_gen_cpp()	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High
CSL Language :: do_not_gen_cpp()	Testing :: Generated	100				Provide generated tests for the current task	High
CSL Language :: gen_unique_rtl_modules()	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High+
CSL Language :: gen_unique_rtl_modules()	Testing :: Generated	100				Provide generated tests for the current task	High+
CSL Autorouter :: connect()	Testing :: Specifications	70				Provide testing specifications (test matrix) for the current task	High+
CSL Autorouter :: connect()	Testing :: Generated	60				Provide generated tests for the current task	High+
CSL Language :: set_clock()	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High++
CSL Language :: set_clock()	Testing :: Generated	100				Provide generated tests for the current task	High++
CSL Language :: register_ios()	Testing :: Specifications	100	31/05/2008			Provide testing specifications (test matrix) for the current task	High++
CSL Language :: register_ios()	Testing :: Generated	100	02/06/2008	09/06/2008		Provide generated tests for the current task	High++
Auto CSL generation	SW :: Support	0				Cslc/misc/projects/csl_ifc_csv_gen / read the README / run the program / in the README file / fix the program / The program needs to do a bottom up traversal to put the top unit at the end of the file so that connect statements do not cause an error / The list of ifc's should be read in and compared to the ifc names in the spreadsheet. / The list of instances in the hier file should match the names in the left column and upper row. / The list of instances in the left column and the upper row need to have the same order.	Low
CSL Language :: Parameters	Documentation :: Spec	90				Documentation readability	Low
CSL Language :: Prefix & Suffix	Documentation :: Spec	50				Documentation readability	Low
CSL Language :: gen_unique_rtl_modules()	Documentation :: Spec	50				Documentation readability	Low
CSL Language :: set_clock()	Documentation :: Spec	50				Documentation readability	Low
CSL Language :: register_ios()	Documentation :: Spec	50				Documentation readability	Low
Docs :: CSL Isa	Documentation :: Spec	60	09/06/2208			Add Derek's markups to document	High++

## N_009
No	Task:	CSLOM implementation support			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: CSLOM				BZ	05/05/2008			90		No end date
	Overall status								90

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_010
No	Task:	CSLOM training class			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: CSLOM				BZ	05/07/2008			30		No end date
	Overall status								30

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_011
No	Task:	Autoruter functionality class			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: Autorouter				BZ	05/07/2008			50		No end date
	Overall status								50

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_012
No	Task:	SystemC codegen			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: SystemC :: translate Verilog modules to entity and architecture				PE	05/12/2008	07/15/2008		0
2	SW :: SystemC :: translate Verilog port/signal declarations				PE	05/12/2008	07/15/2008		0
3	SW :: SystemC :: translate Verilog module instances				PE	05/12/2008	07/15/2008		0
4	SW :: SystemC :: translate Verilog formal to actual mappings				PE	05/12/2008	07/15/2008		0
5	SW :: SystemC :: translate Verilog module parameters				PE	05/12/2008	07/15/2008		0
6	SW :: SystemC :: translate Verilog initial blocks				PE	05/12/2008	07/15/2008		0
7	SW :: SystemC :: translate Verilog always blocks				PE	05/12/2008	07/15/2008		0
8	SW :: SystemC :: translate Verilog conditionals (if else, case)				PE	05/12/2008	07/15/2008		0
9	SW :: SystemC :: translate Verilog for loops				PE	05/12/2008	07/15/2008		0
10	SW :: SystemC :: translate Verilog operators				PE	05/12/2008	07/15/2008		0
11	SW :: SystemC :: translate Verilog expressions				PE	05/12/2008	07/15/2008		0
12	SW :: SystemC :: translate Verilog statements				PE	05/12/2008	07/15/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_013
No	Task:	VHDL Code generator			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: VHDL :: translate Verilog modules to entity and architecture				TH	05/22/2008	06/14/2008		100
2	SW :: VHDL :: translate Verilog port/signal declarations				TH	05/22/2008	06/14/2008		100
3	SW :: VHDL :: translate Verilog module instances				TH	05/22/2008	06/14/2008		100
4	SW :: VHDL :: translate Verilog formal to actual mappings				TH	05/22/2008	06/14/2008		75
5	SW :: VHDL :: translate Verilog module parameters				TH	05/22/2008	06/14/2008		75
6	SW :: VHDL :: translate Verilog initial blocks				TH	05/22/2008	06/14/2008		0
7	SW :: VHDL :: translate Verilog always blocks				TH	05/22/2008	06/14/2008		0
8	SW :: VHDL :: translate Verilog conditionals (if else, case)				TH	05/22/2008	06/14/2008		0
9	SW :: VHDL :: translate Verilog for loops				TH	05/22/2008	06/14/2008		0
10	SW :: VHDL :: translate Verilog operators				TH	05/22/2008	06/14/2008		0
11	SW :: VHDL :: translate Verilog expressions				TH	05/22/2008	06/14/2008		0
12	SW :: VHDL :: translate Verilog statements				TH	05/22/2008	06/14/2008		0
	Overall status								37.5

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_014
No	Task:	Distributed regression			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: Support				OS	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_015
No	Task:	CSIM functionality			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: CSIM				BZ	05/22/2008	05/31/2008		50
	Overall status								50

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_016
No	Task:	Coverage tool evaluation			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: Support				BZ	05/22/2008	05/31/2008		100
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_017
No	Task:	CSL Language :: Support for X and Z in numbers			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			MH	05/22/2008	05/26/2008		80
		Examples							N/A
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CSLOM CMD						N/A
			CSLOM		AS	05/22/2008	05/31/2008		0
			Instance Tree + autorouter						N/A
			CSLOM Design Checker						N/A
			Adapter						N/A
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications							N/A
		Generated tests							N/A
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								40

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_018
No	Task:	Memory Map specification			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation :: Spec				CGH, AB	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_019
No	Task:	ISA specification			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation :: Spec				CGH, AB	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_020
No	Task:	Auto CSL generation			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: Support				OB	05/26/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_021
No	Task:	Marked up documents			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Docs :: CSL Isa				OB				60
2	Docs :: CSL Language				MH				90
	Overall status								75

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_022
No	Task:	iverilog install			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Support				CA				100
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet