## Sheet1
Owner:	Andrei Susnea
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for concat and replication	High++	Also added getWidth for concat and replication in CSLOM | 80% because it needs testing
CSL Language :: Parameters	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for parameters	High+
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for prefix & suffix	High
CSL Language :: do_not_gen_rtl()	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for do_not_gen_rtl()	High	N/A
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for do_not_gen_cpp()	High	N/A
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for do_not_gen_cpp()	High	N/A
CSL Language :: set_clock()	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for set_clock()	High
CSLOM training class	SW :: CSL :: CSLOM	100		Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0		Attend BZ's autorouter functionality presentation	High++
CSL Language :: support for concat in LHS	SW :: CSL :: CSLOM	100		Add support for concat in assignment LHS in CSLOM and CSLOM checker	High++	Also added getWidth for ExprOp
support for X and Z in numbers	SW :: CSL :: CSLOM	0		Add support numbers with X and Z bit values. The spec should be the Verilog standard and MH will add this to CSL Language document	High++