## Sheet1
Owner:	Bogdan Zamfir
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM	100		Implement concat and replication + train OS/EC	High++	Has been implemented in cslom a long time ago
CSL Autorouter :: connect()	Documentation :: Spec	100		Detail current autorouter functionality to CGH	High++	Emails have been sent a long time ago.
CSL Autorouter :: connect()	SW :: CSL :: Autorouter	0		Provide autorouter functionality as in the spec document	High++
CSLOM implementation support	SW :: CSL :: CSLOM	0		Provide support to OS/EC/TH/AS to implement their CSLOM related tasks	High++
Predeclaration bug	All	100		Provide a solution for the predeclaration bug	High++	Solution: Change 75% of parser, cslom, cmd, checker, AutoRouter, instance Tree.
CSLOM training class	SW :: CSL :: CSLOM	0		CSLOM training classes for the following employees: EC, OS, MP, AS, TH, AB (about 1-2 hours/day when at least 80% of the attendees are present at the office)	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0		Hold autorouter functionality presentation for the following employees: AS, EC, AB (about 1 hour/day when at least 60% of the attendees are present at the office)	High++
Coverage tool recommandation	SW :: Support	100		Recommend in a report a coverage tool according to its performance and features (evaluation should contain both a commercial and a free candidate). After the report is compiled please send it to Dinesh and Derek	High++	lcov with a machine farm about 8 cores at least
Coverage tool evaluation	SW :: Support	0	Derek.	Evaluate Bullseye coverage tool	High++	I need Derek to send the evaluation product first
CSIM functionality	SW :: CSL :: CSIM	0		Need solutions and implementations for: single action compile, generated values difference between CSIM and Modelsim (due to flip flop propagation issue) talk to AB/OS for examples, load feature to load stimulus vectors from a file	High++