## Sheet1
Owner:	Monica Helgiu
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	Documentation :: Spec	80		Fix documentation	Med
CSL Language :: Concat & Replication	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	High
CSL Language :: Concat & Replication	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High
CSL Language :: Concat & Replication	Testing :: Generated	100		Provide generated tests for the current task EDIT: updated with all concat tests. Please update your status.	High
CSL Autorouter :: connect()	Documentation :: Examples	100		Write in a temporary doc connect spec provided by DP	High
CSL Language :: do_not_gen_rtl()	Documentation :: Spec	100		Fix documentation	Med
CSL Language :: do_not_gen_rtl()	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	Med
CSL Language :: do_not_gen_cpp()	Documentation :: Spec	100		Fix documentation	Med
CSL Language :: do_not_gen_cpp()	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	Med
CSL Interconnect :: f2a matrix	Documentation :: Specs	100		Interconnect f2a matrix with valid and invalid cases (spec and documentation: interconnect)	High+
CSL Language :: X and Z values spec	Documentation :: Specs	80		Provide specification for numbers with X and Z (use the verilog spec)	High+
CSL Autrouter :: connect()	Documentation :: Specs	50		Fix the presentation for connect methods and current examples	High+