## Sheet1
Owner:	Petronela Ezaru
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: XML Gen	0		Add support for concat and replication	Low	Suspended
CSL Language :: Concat & Replication	SW :: CSL :: PDF Gen	0		Add support for concat and replication	Low	Suspended
CSL Language :: Parameters	SW :: CSL :: XML Gen	0		Add support for parameters	Low	Suspended
CSL Language :: Parameters	SW :: CSL :: PDF Gen	0		Add support for parameters	Low	Suspended
CSL Language :: Prefix & Suffix	SW :: CSL :: XML Gen	0		Add support for prefix & suffix	Low	Suspended
CSL Language :: Prefix & Suffix	SW :: CSL :: PDF Gen	0		Add support for prefix & suffix	Low	Suspended
CSL Language :: Parameters	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Parameters	Testing :: Generated	100		Provide generated tests for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Generated	20		Provide generated tests for the current task	High++
CSL Language :: set_clock()	Testing :: Specifications	0		Provide testing specifications (test matrix) for the current task	High++	Moved task to OB
CSL Language :: set_clock()	Testing :: Generated	0		Provide generated tests for the current task	High++	Moved task to OB
CSL Language :: register_ios()	Testing :: Specifications	0		Provide testing specifications (test matrix) for the current task	High++	Moved task to OB
CSL Language :: register_ios()	Testing :: Generated	0		Provide generated tests for the current task	High++	Moved task to OB
CSL Autorouter :: connect()	Testing :: Specifications	0		Provide testing specifications (test matrix) for the current task	High+
CSL Autorouter :: connect()	Testing :: Generated	0		Provide generated tests for the current task	High+
SystemC codegen	SW :: SystemC :: generator	0		Read SystemC documentation and understand CSL vs SystemC implementations of interconnect	High
SystemC codegen	SW :: SystemC :: generator	0		Ensure and provide SystemC generator interconnect support	High
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Verilog define generator	100		Add support for do_not_gen_rtl() in the Verilog define generator	High+