## Sheet1
NO.	Date	Name	Component	Issue	Release	Status
1	12/08/07	AB	TW	Pipeline	1	NS
2	12/08/07	AB	TW	Stmt	1	IP
3	06/08/07	AB	TW	Test Register	1	NS
4	09/08/07	AB	TW CSLOM	Comment Code	1	IP
5	12/08/07	AB		competitive analysis spreadsheet	1	IP
6	12/08/07	AB/DP	WebSite	create documentation content for web site	1	IP
7	12/08/07	Ada	WebSite	design initial website framework	1	NS
8	08/09/07	Ada	webSite	please check in your code	1	NS
9	08/09/07	Ada	webSite	please set up a SVN repo for the external web site	1	NS
10	12/08/07	Ada	WebSite	plug in content to framework	1	NS
11	12/08/07	Ada	WebSite	study competitors web sites	1	NS
12	07/09/07	Adaptor Team	Adaptor	generate hierarchical decoders connected to registers associated with ISA's	1	NS
13	07/09/07	Adaptor Team	Adaptor	memory map read muxes	1	NS
14	12/08/07	AI	Preprocessor	CSL preprocessor with regex generation	2	NS
15	12/08/07	AI		after tb/vc is working generate a C++ simulator skeleton	1	NS
16	12/08/07	AI	C++ Codegen	decoder	1	NS
17	12/08/07	AI	C++ Codegen	expression	1	NS
18	12/08/07	AI	C++ Codegen	Fifo	1	NS
19	12/08/07	AI	C++ Codegen	interconnect	1	NS
20	12/08/07	AI	C++ Codegen	isa	1	NS
21	12/08/07	AI	C++ Codegen	Pipeline	1	NS
22	12/08/07	AI	C++ Codegen	Register	1	NS
23	12/08/07	AI	C++ Codegen	rf	1	NS
24	12/08/07	AI	C++ Codegen	Stmt	1	NS
25	12/08/07	AI	C++ Codegen	Tb	1	NS
26	12/08/07	AI	C++ Codegen	Vc	1	NS
27	12/08/07	AI	C++ sim Codegen	decoder	1	IP
28	12/08/07	AI	C++ sim Codegen	enum	1	IP
29	12/08/07	AI	C++ sim Codegen	expression	1	IP
30	12/08/07	AI	C++ sim Codegen	field	1	IP
31	12/08/07	AI	C++ sim Codegen	Fifo	1	IP
32	12/08/07	AI	C++ sim Codegen	interconnect	1	IP
33	12/08/07	AI	C++ sim Codegen	isa	1	IP
34	12/08/07	AI	C++ sim Codegen	memmap	1	IP
35	12/08/07	AI	C++ sim Codegen	Pipeline	1	IP
36	12/08/07	AI	C++ sim Codegen	Register	1	IP
37	12/08/07	AI	C++ sim Codegen	rf	1	IP
38	12/08/07	AI	C++ sim Codegen	Stmt	1	IP
39	12/08/07	AI	C++ sim Codegen	Tb	1	IP
40	12/08/07	AI	C++ sim Codegen	Vc	1	IP
41	12/08/07	AO	DocGen	field	1	IP
42	12/08/07	AO	DocGen	Fifo	1	IP
43	12/08/07	AO	DocGen	interconnect	1	IP
44	12/08/07	AO	DocGen	isa	1	IP
45	12/08/07	AO	DocGen	memmap	1	IP
46	12/08/07	AO	DocGen	Pipeline	1	IP
47	12/08/07	AO	DocGen	Register	1	IP
48	12/08/07	AO	DocGen	rf	1	IP
49	12/08/07	AO	DocGen	Stmt	1	IP
50	12/08/07	AO	DocGen	Tb	1	IP
51	12/08/07	AO	DocGen	Vc	1	IP
52	21/08/07	AO	PDF Doc Generator	build docVisitor base class	1	IP
53	21/08/07	AO	PDF Doc Generator	build docVisitor child class	1	IP
54	21/08/07	AO	PDF Doc Generator	build htmlVisitor child class	1	IP
55	21/08/07	AO	PDF Doc Generator	build mifVisitor child class	1	IP
56	21/08/07	AO	PDF Doc Generator	build pdfVisitor child class	1	IP
57	21/08/07	AO	PDF Doc Generator	build XML parser for doc.xml	1	IP
58	09/08/07	AO	PDF Doc Generator	Code the generator	1	IP
59	09/08/07	AO	PDF Doc Generator	CSL cmds	1	IP
60	21/08/07	AO	PDF Doc Generator	Look at CSL warn error code.	1	IP
61	09/08/07	AO	PDF Doc Generator	Specifications for the output files	1	IP
62	17/09/07	AO		see if you can generate C++ const ints for the ISA	1	NS
63	17/09/07	AO		then see if you can generate shift and mask functions for ISA	1	NS
64	12/08/07	AP	Adapter	field	1	IP
65	09/08/07	AP	Adapter	Implement Field	1	IP
66	09/08/07	AP	Adapter	Implement ISA	1	NS
67	09/08/07	AP	Adapter	Implement STATE DATA	1	NS
68	09/08/07	AP	Adapter	Implement Testbench	1	IP
69	09/08/07	AP	Adapter	Implement Verification Components	1	IP
70	12/08/07	AP	Adapter	isa	1	NS
71	12/08/07	AP	Adapter	memmap	1	IP
72	12/08/07	AP	Adapter	Pipeline	1	NS
73	12/08/07	AP	Adapter	Register	1	IP
74	12/08/07	AP	Adapter	Tb	1	IP
75	12/08/07	AP	Adapter	Vc	1	IP
76	18/09/07	AP	Adapter	warn error needs to be included in the adaptor	1	IP
77	09/08/07	AP	Adaptor	Comment Code	1	IP
78	09/08/07	AS/MP	CSLOM CMD	Pipeline	1	NS
79	06/08/07	BZ	AutoMapper	?	2	NS
80	06/08/07	BZ	AutoRouter	?	2	NS
81	09/08/07	BZ	CSLOM	Comment Code	1	IP
82	09/08/07	BZ	CSLOM	Implement Pipeline	2	NS
83	07/09/07	C++ simulator team	C++ Simulator	generate hierarchical decoders connected to registers associated with ISA's	1	NS
84	07/09/07	C++ simulator team	C++ Simulator	memory map read muxes	1	NS
85	39424	CA	Lundt build	configure lundt build	1	NS
86	39424	CA	Lundt build	reinstall lundt build	1	IP
87	12/08/07	CA	Lundt build	test lundt build	1	NS
88	06/08/07	CA	Regression	Optimization	1	IP
89	06/08/07	IC/Petronela	Regression	Regression by chapters	1	IP
90	12/08/07	AM		write simple CSL RISC processor	1	IP
91	08/09/07	CA	Windows	the windows need more foam one th toutside to stop the draft; windows need to be plastered	1	NS
92	17/08/07	CA/CC	HW	buy extra memory for Yo computers - Adrian only has 1GB	1	IP
93	17/08/07	CA/CC	HW	buy logitech noise cancelling head phones	1	IP
94	17/08/07	CA/CC	HW	check hydraulics on all chairs	1	IP
95	17/08/07	CA/CC	HW	sell CRT's, YO switch	1	IP
96	17/08/07	CA/CC	HW	sell RAID controller-is the ad placed yet?	1	IP
97	12/09/07	CA/CC		add external web site SVN repo	1	NS
98	29/08/07	AI	Preprocessor	Javadocs support	1	NS
99	12/08/07	AI	Preprocessor	Verilog Preprocessor	1	IP
100	29/08/07	AI	Preprocessor	Xml encrypt	1	NS
101	12/08/07
102	08/09/07
103	06/08/07
104	13/09/07
105	13/09/07
106	13/09/07
107	08/09/07
108	08/09/07
109	08/09/07
110	08/09/07
111	12/08/07
112	09/08/07	CL	C++ Codegen	Comment Code	1	IP
113	12/08/07	CL		after tb/vc is working write the C++ vector/state data generator-will we use a library that Adrian will write?	1	NS
114	12/08/07	Coder	assertion generation	C++ assertions for C++ simulation	2	NS
115	12/08/07	Coder	assertion generation	e lanaguage	2	NS
116	12/08/07	Coder	assertion generation	PSL	2	NS
117	12/08/07	Coder	assertion generation	Vera	2	NS
118	12/08/07	Coder	assertion propagation	propagate assertions through pipelines to other units	2	NS
119	12/08/07	Cristi/AB	SystemC Codegen	decoder	1	IP
120	12/08/07	Cristi/AB	SystemC Codegen	enum	1	IP
121	12/08/07	Cristi/AB	SystemC Codegen	expression	1	IP
122	12/08/07	Cristi/AB	SystemC Codegen	field	1	IP
123	12/08/07	Cristi/AB	SystemC Codegen	Fifo	1	IP
124	12/08/07	Cristi/AB	SystemC Codegen	interconnect	1	IP
125	12/08/07	Cristi/AB	SystemC Codegen	isa	1	IP
126	12/08/07	Cristi/AB	SystemC Codegen	memmap	1	IP
127	12/08/07	Cristi/AB	SystemC Codegen	Pipeline	1	IP
128	12/08/07	Cristi/AB	SystemC Codegen	Register	1	IP
129	12/08/07	Cristi/AB	SystemC Codegen	rf	1	IP
130	12/08/07	Cristi/AB	SystemC Codegen	Stmt	1	IP
131	12/08/07	Cristi/AB	SystemC Codegen	Tb	1	IP
132	12/08/07	Cristi/AB	SystemC Codegen	Vc	1	IP
133	29/08/07	DEV TEAM	-	Expr & f2a in csl	1	NS
134	09/08/07	DEV TEAM	CSL	CSLC Architecture Document	1	NS
135	12/08/07	DP		sign up for serverpronto.com server for stealth website	1	NS
136	09/08/07	DP/BZ		CSL Pipeline Review	1	NS
137	06/08/07	DT	DOCS	CSL Semantics and Language Rules	1	IP
138	15/08/07	DT	DOCS	Patent pictures	1	IP
139	06/08/07	DT	DOCS	Register	1	IP
140	06/08/07	DT	L/P	Test Pipeline	1	NS
141	06/08/07	DT	L/P	Test Register + write ex	1	NS
142	06/08/07	DT	Tests	Check Verification Components in Parser + wrote code for ex.	1	IP

155	12/08/07	MP/AS	CSLOM CMD	Pipeline	1	NS
156	06/08/07	MP/AS	CSLOM CMD	TestBench	1	IP
157	09/08/07	MP/AS	CSLOM CMD	Comment Code	1	IP
158	09/08/07	OS	CSLOM	Comment Code	1	IP
159	12/08/07	OS	L/P	add useful error messages:decoder	1	IP
160	12/08/07	OS	L/P	add useful error messages:enum	1	IP
161	12/08/07	OS	L/P	add useful error messages:expression	1	IP
162	12/08/07	OS	L/P	add useful error messages:field	1	IP
163	12/08/07	OS	L/P	add useful error messages:fifo	1	IP
164	12/08/07	OS	L/P	add useful error messages:interconnect	1	IP
165	12/08/07	OS	L/P	add useful error messages:isa	1	IP
166	12/08/07	OS	L/P	add useful error messages:memmap	1	IP
167	12/08/07	OS	L/P	add useful error messages:pipeline	1	IP
168	12/08/07	OS	L/P	add useful error messages:reg	1	IP
169	12/08/07	OS	L/P	add useful error messages:rf	1	IP
170	12/08/07	OS	L/P	add useful error messages:stmt	1	IP
171	12/08/07	OS	L/P	add useful error messages:tb	1	IP
172	12/08/07	OS	L/P	add useful error messages:vc	1	IP
173	09/08/07	OS	L/P	Comment Code	1	IP
174	12/08/07	OS	L/P	expression	1	IP
175	12/08/07	OS	L/P	stmt	1	IP
176	09/08/07	OS	L/P	TestBench	1	IP
177	09/08/07	OS	L/P	Verification Components	1	IP
178	08/09/07	OS	warn/error	When an error is reported the warning error should be printed, not just the error number	1	NS
179	08/09/07	OS/AO	Warn Error XML files	/directory - remove extra files	1	NS
180	08/09/07	OS/AO	Warn Error XML files	fix the warnerrfinalsmaller.xml	1	NS
181	08/09/07	OS/AO	Warn Error XML files	fix the C++ code generator	1	NS
182	08/09/07	OS/AO	Warn Error XML files	rename the warnerrfinalsmaller.xml to csl_warn_error.xml	1	NS
183	21/08/07	OS/TB	PDF Doc Generator	help out AO this when you return.	1	NS

195	12/08/07	Silvia/CB	Vacation Tool	initialize by Aug 14	1	IP
196	08/09/07	TB		ports should take a width argument-update test gen	1	IP
197	21/08/07	Team	CSLC	Get rifd of extra xml warn error files, keep the one that's usefull	1	NS
198	21/08/07	Team	PDF Doc Generator	team find code obfusctor	1	IP
199	21/08/07	Team	PDF Doc Generator	team find license tool to link into our compiler	1	IP
200	21/08/07	Team	Regression	Lundt build will run the warn error binary over the xml file.	1	NS
201	12/08/07	Team	Vacation Tool	test tool by Aug 18	1	IP
202	08/09/07	Team		find seg faults in generated regression tests	1	NS
203	18/09/07		CodeGen	warn error needs to be included in the code generator	1	IP
204	12/08/07		Regression	csl tests generate verilog code which should be parsed by modelsim	1	IP
205	12/08/07		Regression	csl tests generate verilog code which should then be parsed by cslc	1	IP

207	12/08/07			someone needs to write a C++ simulator using adrian's csim libs	1	NS
208	12/08/07	AB	TW	decoder	1	D
209	12/08/07	AB	TW	enum	1	D
210	12/08/07	AB	TW	expression	1	IP
211	12/08/07	AB	TW	field	1	D
212	12/08/07	AB	TW	Fifo	1	D
213	12/08/07	AB	TW	interconnect	1	D
214	12/08/07	AB	TW	isa	1	D
215	12/08/07	AB	TW	memmap	1	D
216	12/08/07	AB	TW	Register	1	IP
217	12/08/07	AB	TW	rf	1	D
218	12/08/07	AB	TW	Tb	1	IP
219	09/08/07	AB	TW	TestBench	1	IP
220	09/08/07	AB	TW	TestBench Docs	1	IP
221	12/08/07	AB	TW	Vc	1	IP
222	09/08/07	AB	TW	Verification Components	1	IP
223	09/08/07	AB	TW	Verification Components Docs	1	IP
224	06/08/07	AB	TW ISA	Not tottaly implemented – update	1	D
225	09/08/07	AI	C++ Simulator	Libraries	1	IP
226	09/08/07	AI	CLI	Command line binary	1	D
227	09/08/07	AI	CLI	Command line integration with top level	1	NS
228	29/08/07	AI	CmdLine	Unknown CmdLine options	1	NS
229	06/08/07	AI	CmdLine	Verifiy Command Line Parser	1	IP
230	12/08/07	CristiL	C++ Codegen	enum	1	NS
231	12/08/07	AI	C++ Codegen	field	1	D
232	12/08/07	AI	C++ Codegen	Memmap	1	NS
233	12/08/07	AP	Adapter	decoder	1	D
234	12/08/07	AP	Adapter	enum	1	D
235	12/08/07	AP	Adapter	expression	1	D
236	12/08/07	AP	Adapter	interconnect	1	D
237	12/08/07	AP	Adapter	Fifo	1	D
238	12/08/07	AP	Adapter	rf	1	D
239	12/08/07	AP	Adapter	Stmt	1	D
240	09/08/07	AP	Adapter	Update BitRange	1	D
241	29/08/07	AP	Adaptor	SG/Ifc connections problem	1	NS
242	06/08/07	AS	CSLOM	Register	1	IP
243	13/08/07	AS	TaskList	Change name of issueList to TaskList	1	D
244	06/08/07	AS/DT/BZ	CSLOM Field	Design problem	1	D
245	09/08/07	AS/MP	CSLOM CMD	Memory Map – rewrite	1	IP
246	09/08/07	AS/MP	CSLOM CMD	MultiDim BitRange	1	IP
247	09/08/07	AS/MP	CSLOM CMD	Register	1	D
248	09/08/07	AS/MP	CSLOM CMD	Simple BitRange	1	D
249	09/08/07	AS/MP	CSLOM CMD	TestBench	1	IP
250	06/08/07	BZ	CSLOM	?	1	D
251	09/08/07	BZ	CSLOM	Auto Router	1	NS
252	12/08/07	BZ	CSLOM	decoder	1	D
253	12/08/07	BZ	CSLOM	enum	1	D
254	12/08/07	BZ	CSLOM	expression	1	D
255	12/08/07	BZ	CSLOM	field	1	D
256	09/08/07	BZ	CSLOM	Field	1	D
257	12/08/07	BZ	CSLOM	Fifo	1	D
258	09/08/07	BZ	CSLOM	Fix ports/signals/interface/signal groups	1	IP
259	12/08/07	BZ	CSLOM	interconnect	1	D
260	09/08/07	BZ	CSLOM	ISA	1	IP
261	12/08/07	BZ	CSLOM	isa	1	IP
262	12/08/07	BZ	CSLOM	memmap	1	D
263	09/08/07	BZ	CSLOM	Recode BitRange	1	D
264	12/08/07	BZ	CSLOM	Register	1	D
265	12/08/07	BZ	CSLOM	rf	1	D
266	12/08/07	BZ	CSLOM	Stmt	1	D
267	12/08/07	BZ	CSLOM	Tb	1	D
268	12/08/07	BZ	CSLOM	Vc	1	D
269	06/08/07	BZ	CSLOM Field	WARN/ERR Message – rewrite	1	D
270	06/08/07	BZ	CSLOM ISA	Not tottaly implemented – rewrite - target 27.08	1	IP
271	12/08/07	CA/CC	Regression	create MySQL database to store results	1	IP
272	06/08/07	CC	ANTLR	ANTLR turn off Trace (option)	1	D
273	06/08/07	CC/AI	CmdLine	Test executable w| command line to sent to California	1	IP
274	09/08/07	CL	CSLOM C++ code gen	Generate constants for fields	1	D
275	09/08/07	CL	CSLOM C++ code gen	Generate field functions	1	D
276	08/09/07	DEV TEAM		ports should take a width argument-update LPW/CSLOM cmd	1	NS
277	17/09/07	DOCS	DOCS	add a section to the language manuals which shows which objects can be instantiated in each class	1	NS
278	12/08/07	DOCS		clean up the manuals directory-move some files to app notes	1	D
279	12/08/07	DOCS		make parallel directory to manuals called app notes	1	D
280	12/08/07	DOCS		mark reserved words with index text marker in fm docs	1	D
281	12/08/07	DOCS		split manuals/*fm files into language and app notes fm files	1	D
282	08/09/07	DOCS Team	DOCS	Add a cmd description for each of the following cmds: vector_name.set_module_name(unit_instance); vector_name.set_direction(direction); vector_name.exclusion_list(connection_elements);vector_name.include_only(connection_elements);	1	NS
283	08/09/07	DOCS Team	DOCS	Add a crossref on each command page back to the cmd summary	1	NS
284	08/09/07	DOCS Team	DOCS	ports should take a width argument-update docs	1	NS
285	21/08/07	DP	CSLC	reviewed Perl regression code and gave Petronela action items.	1	D
286	21/08/07	DP	CSLC	reviewed the csl_register cmd summary and gave Andrei B action items	1	D
287	21/08/07	DP	CSLC	reviewed the csl_vc cmd summary and gave AndreiS action items.	1	D
288	21/08/07	DP	CSLC	reviewed the cslc C++ cod gen and C++ simulation classes regression code and gave Cristi action items.	1	D
289	21/08/07	DP	CSLC	reviewed the cslc top level regression code and gave Adrian action items.	1	D
290	21/08/07	DP	CSLC	spoke with AM/Monica about verilog and gave them the action item of building a pipeline and test bench in verilog and simulating it in Modelsim	1	D
291	21/08/07	DP	CSLC	spoke with Mr. Haba about the processor ring and gave him the task of building the processor ringI	1	D
292	12/08/07	DP/AB		review the tb and vc docs	1	D
293	06/08/07	DT	CSL Prefix/Interconnect	Test	1	D
294	09/08/07	DT	DOCS	FM docs – fix	1	IP
295	06/08/07	DT	Tests	Check ISA in Parser	1	D
296	29/08/07	MH	DOCS	Add logicf reset/clock	1	NS
297	08/09/07	MH/DT/AM	DOCS	released pdf cmd summary links not working in all docs	1	NS
298	06/08/07	Monica	DOCS	Memory Map	1	D
299	12/08/07	MP/AS	CSLOM CMD	decoder	1	D
300	12/08/07	MP/AS	CSLOM CMD	enum	1	D
301	12/08/07	MP/AS	CSLOM CMD	expression	1	D
302	12/08/07	MP/AS	CSLOM CMD	field	1	D
303	12/08/07	MP/AS	CSLOM CMD	Fifo	1	D
304	12/08/07	MP/AS	CSLOM CMD	interconnect	1	D
305	12/08/07	MP/AS	CSLOM CMD	isa	1	IP
306	12/08/07	MP/AS	CSLOM CMD	memmap	1	IP
307	12/08/07	MP/AS	CSLOM CMD	Register	1	D
308	06/08/07	MP/AS	CSLOM CMD	Register – test	1	NS
309	12/08/07	MP/AS	CSLOM CMD	rf	1	D
310	12/08/07	MP/AS	CSLOM CMD	Stmt	1	D
311	12/08/07	MP/AS	CSLOM CMD	Vc	1	NS
312	06/08/07	MP/AS	CSLOM CMD	Verification Components	1	NS
313	18/09/07	MP/AS	CSLOM CMD	warn error needs to be included in the CSLOM cmd	1	IP
314	06/08/07	MP/AS	CSLOM CMD ISA	Not implemented	1	IP
315	06/08/07	MP/AS	CSLOM CMD MemoryMap	Not implemented – rewrite	1	IP
316	12/08/07	OS	L/P	decoder	1	D
317	12/08/07	OS	L/P	enum	1	D
318	12/08/07	OS	L/P	field	1	D
319	12/08/07	OS	L/P	fifo	1	D
320	12/08/07	OS	L/P	interconnect	1	D
321	12/08/07	OS	L/P	isa	1	D
322	12/08/07	OS	L/P	memmap	1	D
323	12/08/07	OS	L/P	reg	1	D
324	12/08/07	OS	L/P	rf	1	D
325	09/08/07	OS	L/P	Run regression / fix bugs	1	IP
326	12/08/07	OS/AB/TB/BZ/AP		get tb/'vc working	1	IP
327	12/08/07	Petronela	Regression	add code gen chapter support in single threaded regression script	1	IP
328	12/08/07	Petronela	Regression	fix bugs in single threaded regression script	1	D
329		Petronela	Regression	Regression html optimization
330	13/09/07	Petronela/Ines	Regression	move the script to TOT/misc/scripts	1	IP
331	13/09/07	Petronela/Ines	Regression	remove all of the old scripts in svn/misc/test/parser/scripts/	1	IP
332	13/09/07	Petronela/Ines	Regression	rename the script run_regress.pl	1	IP
333	06/08/07	TB	CodeGen	Bugs CSL FIFO	1	D
334	06/08/07	TB	CodeGen	Division into chapters	1	D
335	06/08/07	TB	CodeGen	Field + SetRange	1	D
336	06/08/07	TB	CodeGen	Hierarchical Semantic Checks	1	IP
337	06/08/07	TB	Manual tests	2 bitrange manual test fail	1	D
338	06/08/07	TB/DT/AM	DOCS	TestBench Doc Review	1	D
339	06/08/07	TB/DT/AM	DOCS	Verification Components Doc Review	1	D
		CC/CA	IT	Cd rom automount
		CC/CA	IT	Nightly build to generate tests
		CC/CA	IT	Download tests to machines
		CC/CA	IT	Talk to ines about verilog regression
		CC/CA	IT	FTP box and binary: We need to send a binary ASAP with CLI, CDOM, and the verilog parser and code gen to California. Please make a new build.xml target.
		CC/CA	IT	inform NLP of domain name change
		CC/CA	IT	Check library licences

		CC/CA	IT	Talk with AB about security issues			Check email
		CC/CA	IT	Check who has repo home

		CC/CA	IT	Give docs guys access to bin
		CC/CA	IT	Look for gnu position to static linking
		CC/CA	IT	Setup script for dyn cslc
		CC/CA	IT	Check ines' monitor
		CC/CA	IT	Bugzilla reassign

		CC/CA	IT	Bugzilla graphs			bugzilla generate graphs on users request

		CC/CA	IT	Webmail certificate is still fastpathlogic.ro
		CC/CA	IT	svn: REPORT request failed on '/svn/TOT/!svn/vcc/default / svn: REPORT of '/svn/TOT/!svn/vcc/default': Compressed response was truncated (http://build)'

		IC/PE	Regression	Generate test by chapter.
		IC/PE	Regression	Test by chapter.
		IC/PE	Regression	Test by manual.
		IC/PE	Regression	Test by lang_docs.
		IC/PE	Regression	Test by tb_generate.
		IC/PE	Regression	Test by Big_test.
		IC/PE	Regression	Test by invalid.
		IC/PE	Regression	Test by valid.
		CC/CA	IT	DNS cache for both locations for use by the crawler / -increase cache size / -increase time out to remove DNS entry

		CC/CA	IT	Adrian passwd on bugzilla

		CC/CA	IT	Make luntbuild results accessible from outside
		CC	IT	Bugzilla collation issue
		CC/CA	IT	Install apache on regression machines for results
		CC/CA	IT	Install 32bit machines for compiling
		CC	IT	Vacation tool revamp
		CC	IT	Install new build machine
		CC	Build	Install luntbuild on all machines and run a nightly regression on all machines with valgrind (different directories on each machine so it finishes in one night)
		CC/CA	IT	DNS cache for both locations for use by the crawler / -increase cache size / -increase time out to remove DNS entry
		CC/CA	IT	use P3 machine for DNS server
		CC/CA	IT	Shut off the following services at FPL: / Yahoo IM / Google IM / MSN / All IM proxies / Youtube / All other video sharing sites / Shut off any other non-work related sites. / Perhaps you can just select a few sites that people need to look up HW and C++ answers.
		CC	IT	Set up luntbuild at YO
		CC/CA	IT	Add repo for the external web page
		CC	IT	Set up routing for the different internet lines
		CC	IT	Set up internal web server for the crawler to work on
		CA	IT	Set up crawlers to work with the internal web server
		CA	IT	Luntbuild: Error: JAVA_HOME is not defined correctly.
		CA	IT	Luntbuild email Problem while sending mime mail:
				at org.apache.tools.ant.taskdefs.email.MimeMailer.send(MimeMailer.java:231)
		CC/CA		reinstall lundtbuild and get it working	1	NS
		CC	Vacation Tool	new version by Aug 13	1	IP

		CC/AI/OS	Preprocessor+CmdLine	Integration of command line preprocessor cslc	1	IP
		CC/CA	Bugzilla	Bugzilla security	1	IP
		CC/CA	Bugzilla	Fix bugzilla reassign problem	1	IP
		CC	IT	build.xml release target
		CC	IT	Please create a chron job to create the ant v2v binary nightly and add it to the ftp box.
		CC	Build	Nightly built CSLC(Verilog) should go in the FTP dropbox
		CC	IT	Mail the status link every night
		CC	IT	FAQ about build system (ant) and add to int website
		CA	IT	svn class: add, revert, update, info, log, move, del, / outdated file, lock, unlock, conflict
		CC	IT	I will make an authenticable proxy server. The people that NEED internet access can then log on with their username and password. All traffic WILL BE LOGGED so that abusers can be tracked down.
		AndreiS		Andrei give CC specific (e.g. URL's for music sites).
		CC	IT	Claudiu everyone needs access to their school email accounts.
		CC/CA	lundt build	Login to access the luntbuild results from outside of the company	1	IP
		CC/Petronela	Regression	create new distributed regression script	1	IP
		CC/CA	IT	Need switch user added to Gnome login screen / just like KDE login switch user
		CC	IT	Setup lint
		CC/CA	IT	check in a release cslc binary for use by HW team
		CC/CA	IT	SVN: remove source code access for anyone except / developers and anyone running GDB
		CC	IT	Move all offtopic shit out of the CSLOm directory
		CC/CA	IT	Rewire office with cat6
		CC/CA	IT	Fpl64-08 reinstall
		CC/CA	/	build.xml: create executable with cli cdom verilog codegen
		CA	IT	Inventory sheets – update with new computers
		CC/CA	IT	32bit linux build
		CC/CA	IT	32bit windows build
		CC/CA	IT	64bit windows build
		CC/CA	IT	32bit we.xml lib
		CC/CA	IT	add ssh-agent to all machines
		CC	IT	open 8080 port and check luntbuild links sent by mail
		CC	IT	[luntbuild] build of "CSLC/Release/cslc-0.1 (build 72)" failed
		CC	IT	luntbuild: call graph_regress.pl and send email / to group with the location of the / graph_regress.pl png output files.
		CC	IT	CSL Regression[ ]Can't locate object method "new" via package "MIME::Lite" (perhaps you forgot to load "MIME::Lite"?) at /srv/luntbuild/work/CSLC/trunk/scripts/run_regress.pl line 1719. CSL Regression[ ]REGRESSION DONE ! [ ]Command builder failed: build success condition not met!
		CC	IT	luntbuild nightly: call run_regress.pl -hdl verilog
		CC	IT	luntbuild nightly: call run_regress.pl -hdl csl_v2
		CC	IT	ftp instructions to dep and CA engineers
		CC	IT	distributed regressions using ssh and run_regress.pl -valgrind on all machines at night
		CC	IT	luntbuild bug: must ant clean before running ant
		CC	IT	need dedicated channel btwn fpl and yoterra
		CC	IT
		CC	IT
		CC	IT	create windows build.xml files
		CC	IT	add luntbuild to all new linux distro servers
		CC	IT	fix email problem with run_regress.pl on luntbuild
		CC/CA	IT	shut off write access to trunk/test/csl for everyone except bz, as, ab, mp, tb, dp, ca, os, ap
		IS/P	testing	add vf file support to the run_regress.pl script
		IS/P	testing	run_regress.pl script: add support for running cpp code, verilog testbench/DUT code
		IS/P	testing	testgen: memory map and all obejct types, all combinations of memory map cmds with / all error conditions for memory map addresses
		IS/P	testing	testgen: testbench and all obejct types, all combinations of test bench cmds with / cpp Csim code
		IS/P	testing	new script to read the chapter results and create a summary HTML page. / to be used by the distributed regression to post process the results.
		IS/P	testing	test the Csim generated code. Does make work? Compiles with no errors?
		IS/P	testing	test the Csim generated code. Add C++ logic to simulate a chip. does it work?
		IS/P	testing	test the Csim generated code. Generate vectors and use to drive a tb/dut. Works?
		IS/P	testing	test the Csim generated code. Generate SD and use to test a tb/dut. Works?
		IS/P	testing	test the Csim generated code. Generate SD and use to test a tb/dut. Works?
		IS/P	testing	modify the mem map test gen to work with the new syntax. / Memory map pages have a set_unit_name command now. / Memory map pages are not instantiated in memory map any more. / Flat memory has been removed.
		IS/P	testing	testgen: ISA tests.
		IS/P	testing	fix generated tests for memory map && memory map page-use abreviations
		test team	testing	Go through all invalid tests which are passing. Figure out if the test is written correctly. If it is and no bug has been filed then file a bug.
		test team	testing	Add the missing CSL code to the doc examples.
		test team	testing	Write additional invalid tests.
		test team	testing	Test Alina's generated Verilog testbench code.
		test team	testing	Write C++ code to plug into the generated C++ simulator and generate vectors for the generated testbench. Write an equivalent design in verilog using the generated verilog code. Then use the vectors to verify the verilog dut.
		test team	testing	Write some complex CSL tests to stress the system. Make sure that they are parsed without error.
		test team	testing	write test to test the cslc checker.

		test team	testing	AndreiS test plan: implement it
184	08/09/07	P/Ines/CA	Regression	distributed regression script-divide the list of tests into batch jobs which are run on different machines.	1	NS
185	08/09/07	P/Ines/CA	Regression	distributed regression script-results are pulled from the machine and aggregated on the machine running the post processing script.	1	NS
186	08/09/07	P/Ines/CA	Regression	distributed regression script-The post processing script will poll the machines to see if the run_<pid> file has been written.	1	NS
187	08/09/07	P/Ines/CA	Regression	distributed regression script-The results of each run is stored on the respective machines the jobs were run on.	1	NS
188	08/09/07	P/Ines/CA	Regression	distributed regression script-When the job is completed the run script will write out a file with the name run_<pid>.	1	NS
189	08/09/07	P/Ines/CA	Regression	regression script-pass arguments to functions and eliminating the global variables.	1	IP
190	08/09/07	P/Ines/CA	Regression	regression script-split the current regression script into execute and a post process scripts.	1	NS
191	12/08/07	Petronela	Regression	compare the current regression against a specified regression result	1	IP
192	12/08/07	Petronela	Regression	compare the current regression against the previous night's regression results	1	NS
193	12/08/07	Petronela	Regression	generate HTML pages from database	1	NS
194	12/08/07	Petronela	Regression	modify existing script to work with database	1	NS
		IC/PE	IT	Build status Extra: total lines of C++/antlr lines of / code in the project – script
		IC/Petronela	Regression	Write a script to graph the results of the last n / regressions Add GD::graph to the perl script
		IC/Petronela	Regression	Write a script to compare the last two regressions / did the new regression get better or worse
143	12/08/07	HW Team	WebSite	create Flash content for web site	1	IP
144	12/08/07	HW Team		AMBA bus	2	NS
145	12/08/07	HW Team		AXI bus	2	NS
146	12/08/07	HW Team		bus interface unit	2	NS
147	12/08/07	HW Team		MBIST CSL code	2	IP
148	12/08/07	HW Team		OCP bus	2	NS
149	12/08/07	HW Team		simulate and debug processor ring	1	IP
150	12/08/07	HW Team		test unit	2	NS
151	12/08/07	HW Team		update processor ring CSL code	1	IP
152	12/08/07	Ines		test the generated C++ code	1	IP
153	12/08/07	Ines/DT/AM		someone needs to start simulating the generated verilog code	1	NS
154	07/09/07	Ines/Petronela	Regression	Regression should be able create a comparison between the current run and the previous run.	1	IP
		IC/PE	IT	Modify the bug graphs to reflect more categories
		HW Team		download more verliog tests from the net
		OS/AO		get warn error XML file fixed
155		AO	Testing	write enum tests that use verilog numbers in enums
156		AO	Testing	write a set of enum tests that use verilog numbers in enums and fields to check the widths.
157		AO	Testing	write a set of tests with numbers only and put them in a numbers dir
		CA/MD	IT	BUY POWER STRIPS AND PUT IN ROOMS / WHERE THEY ARE NEEDED:Adrian's computer / Petronela's computer
		CA	IT	install: Trac is an enhanced wiki and issue tracking system / for software development projects: http://trac.edgewall.org/
		CA	IT	install icalendar server

		CC	IT	build.xml: Put binary snapshot in svn (separate release dir)
		CC	IT	Fix and optimize build.xml files
		CC	IT	Generate tests in build.xml target
		CC	Warn Error XML files	add a rule to the ant build.xml file to check in the current WE object file
		CC/CA/TB		If the warn error XML file is updated and if the build succeeds the XML must be checked into SVN
		CC/CA/TB		Warn error XML file must be compiled every night by luntbuild
		CC	IT	svn release tagging (check on net for it)
		CC	IT	build.xml files: replace the 10+ copies of the same / build.xml fie that have slight variations with a single / template file. Ask CB for details.
		CC	IT	send email with ftp download instructions to Inder, Melesse, and Hernan, and cc me.
		CC/CA	IT	SVN line counting program which generates a weekly report / called by luntbuild on sunday nights / emails graphs to managers			http://www.statsvn.org/index.html - open source / commercial tools / http://www.polarion.com/ / http://www.smartbearsoftware.com/codereports.php / CodeReports v1.1 (one user) $1,999.95
		CC	IT	add cf file support to the run_regress.pl script
		CC	CSLC	Resolve the enum problem in the WE header
		CC	CSLC	Build cslc on old Redhat/Suse
		CC	CSLC	Build cslc on Debian
		CC	CSLC	Run regression on Debian
		CC	IT	SVN FAQ File
		CC	CSLC	Windows build
		CC	CSLC	Windows cslc regressions
		CC/TB	CSLC	V2V target support
		CC	CSLC	Move libraries out of /opt/tools into the svn repo
		CC/BZ	CSLC	Eliminate internal boost libs. Use the ones supplied with the OS
		CC	IT	Modify the luntbuild templates to include links
		CC	IT	Make a script that checks the library versions on the clients' computers and outputs if the environment is sane for running the CSLC
		CC	IT	Replace LDAP fan/PS
		CC	IT	Memory checkers: Heap agent, Microquill, purify++ (IBM/Rational), bounds checker (compuware)
		CC	IT	Dist_regress.pl – Fix generation of the main summary page from the chapter directory summary.txt files (ask BZ)