## Sheet1
Owner:	Andrei Branzila
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: Treewalker	100				Add support for concat and replication	High++
CSL Language :: Concat & Replication	Testing :: Regression :: golden	0				Add tests from new to golden after all components comply	Low
CSL Language :: Parameters	SW :: CSL :: Treewalker	90				Add support for parameters	High
CSL Language :: Prefix & Suffix	SW :: CSL :: Treewalker	100				Add support for prefix & suffix	High
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: Treewalker	100				Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: Treewalker	100				Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: Treewalker	0				Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	50				Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0				Attend BZ's autorouter functionality presentation	High++
Memory Map specification	Documentation :: Spec	0				Provide specification for memory map with CGH	High++
ISA specification	Documentation :: Spec	0				Revise/Fix/Rewrite specification for ISA with CGH (check consistency between SW implementation and current documentation)	High++
CSL Autorouter :: connect() method	SW :: CSL :: Treewalker	100				Add support for all connect methods as described in auto router document (Current connect variants sub-chapter: pages 14-16)	High++
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Treewalker	100				Add support for do_not_gen_cpp()	High