## Sheet1
Owner:	Bogdan Zamfir
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM	100				Implement concat and replication + train OS/EC	High++	Has been implemented in cslom a long time ago
CSL Autorouter :: connect()	Documentation :: Spec	100				Detail current autorouter functionality to CGH	High++	Emails have been sent a long time ago.
CSL Autorouter :: connect()	SW :: CSL :: Autorouter	100	06/05/2008	06/12/2008		Provide autorouter functionality as in the spec document	High++	Done.
CSLOM implementation support	SW :: CSL :: CSLOM	90				Provide support to OS/EC/TH/AS to implement their CSLOM related tasks	High++	I am waiting for questions and problems
CSLOM training class	SW :: CSL :: CSLOM	90				CSLOM training classes for the following employees: EC, OS, MP, AS, TH, AB (about 1-2 hours/day when at least 80% of the attendees are present at the office)	High++	Held the class, explained about everything i could, I'm waiting for questions
Autoruter functionality class	SW :: CSL :: Autorouter	0			AS, EC	Hold autorouter functionality presentation for the following employees: AS, EC, AB (about 1 hour/day when at least 60% of the attendees are present at the office)	High++	they have exams and school projects
Coverage tool evaluation	SW :: Support	100	06/02/2008	06/03/2008		Evaluate Bullseye coverage tool	High++	Bad report system, no improvement next to lcov
CSIM functionality	SW :: CSL :: CSIM	50	06/03/2008	06/05/2008	specs	Need solutions and implementations for: single action compile, generated values difference between CSIM and Modelsim (due to flip flop propagation issue) talk to AB/OS for examples, load feature to load stimulus vectors from a file	High++	Implemeted execute order in simulator and support in shell, Still need implementation of CLI for csim binary