## Sheet1
Owner:	Mihaela Plaesu
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM_cmd	80				Add support for concat and replication	High++
CSL Language :: Concat & Replication	SW :: CSL :: Adapter	90				Add support for concat and replication	High++	Needs some testing
CSL Language :: Parameters	SW :: CSL :: CSLOM_cmd	0			CSLOm support needed	Add support for parameters	High+
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM_cmd	90			CSLOm support needed	Add support for prefix & suffix	High
CSL Language :: Prefix & Suffix	SW :: CSL :: Adapter	30				Add support for prefix & suffix	High
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM_cmd	100			CSLOm support needed	Add support for do_not_gen_cpp()	High
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM_cmd	100			CSLOm support needed	Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: CSLOM_cmd	80			CSLOm support needed	Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: CSLOM_cmd	50			CSLOm/TW support needed	Add support for register_ios()	High
CSL Language :: register_ios()	SW :: CSL :: Adapter	0				Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	100				Attend BZ's CSLOM training classes	High++