## Sheet1
Owner:	Petronela Ezaru
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Parameters	Testing :: Generated	100				Provide generated tests for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Generated	90				Provide generated tests for the current task	High++
SystemC codegen	SW :: SystemC :: generator	0				Read SystemC documentation and understand CSL vs SystemC implementations of interconnect	High
SW :: SystemC :: translate Verilog modules	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog port/signal declarations	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog module instances	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog formal to actual mappings	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog module parameters	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog initial blocks	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog always blocks	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog conditionals (if else, case)	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog for loops	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog operators	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog expressions	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High
SW :: SystemC :: translate Verilog statements	SW :: SystemC :: generator	0				Ensure and provide SystemC generator interconnect support	High