## Sheet1
Owner:	Tiberiu Haret
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	SW :: CSL :: Adapter	50			TW	Add support for parameters	High
CSL Language :: do_not_gen_cpp()	SW :: Main :: CLI	0			Specs	Add support for do_not_gen_cpp()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Adapter	100				Add support for do_not_gen_cpp()	High
CSL Interconnect :: gen_unique_rtl_module()	SW :: CSL :: Adapter	100				Add support for gen_unique_rtl_module()	High
CSLOM training class	SW :: CSL :: CSLOM	100				Attend BZ's CSLOM training classes	High++
CSL Interconnect :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM	100			Specs	Add support for gen_unique_rtl_modules()	High+
SW :: VHDL :: translate Verilog modules to entity and architecture	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High	still lots to learn about both Verilog and VHDL, so it's going to take me some time to implement this
SW :: VHDL :: translate Verilog port/signal declarations	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog module instances	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog formal to actual mappings	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog module parameters	SW :: CDOM :: VHDL code generator	100	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog initial blocks	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	Low	Low Due to DP's request based on CSL current support
SW :: VHDL :: translate Verilog always blocks	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	Low	Low Due to DP's request based on CSL current support
SW :: VHDL :: translate Verilog conditionals (if else, case)	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	Low	Low Due to DP's request based on CSL current support
SW :: VHDL :: translate Verilog for loops	SW :: CDOM :: VHDL code generator	0	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	Low	Low Due to DP's request based on CSL current support
SW :: VHDL :: translate Verilog operators	SW :: CDOM :: VHDL code generator	75	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog expressions	SW :: CDOM :: VHDL code generator	75	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High
SW :: VHDL :: translate Verilog statements	SW :: CDOM :: VHDL code generator	25	05/22/2008	06/14/2008		Implement a VHDL code generator for interconnect	High