## TaskMap
TaskID	Name	Link	Overall Status
N_001	CSL Language :: Concat & Replication	N_001	83.82

N_002	CSL Language :: Parameters	N_002	77
N_003	CSL Language :: Prefix & Suffix	N_003	77.33
N_004	CSL Language :: do_not_gen_rtl()	N_004	100
N_005	CSL Language :: do_not_gen_cpp()	N_005	90.91
N_006	CSL Language :: gen_unique_rtl_modules()	N_006	85
N_007	CSL Language :: set_clock()	N_007	61.67
N_008	CSL Language :: register_ios()	N_008	23
N_009	CSL Autorouter :: connect() method	N_009	63
N_010	CSLOM implementation support	N_010	0
N_011	Predeclaration bug	N_011	100
N_012	CSLOM training class	N_012	50
N_013	Autoruter functionality class	N_013	0
N_014	CSLOM implementation support	N_014	0
N_015	Adapter prefix bug (duplicate port bug)	N_015	100
N_016	SystemC codegen	N_016	0
N_017	Interconnect F2A valid/invalid cases matrix	N_017	100
N_018	Support for concat in assignment LHS	N_018	100
N_019	CSLOm Visitor traversal functions update	N_019	100
N_020	Coverage tool recommandation	N_020	100
N_021	VHDL Code generator	N_021	15
N_022	Distributed regression	N_022	0
N_023	CSIM functionality	N_023	0
N_024	Coverage tool evaluation	N_024	0
N_025	CSL Language :: Support for X and Z in numbers	N_025	40
N_026	Memory Map specification	N_026	0
N_027	ISA specification	N_027	0
N_028	Auto CSL generation	N_028	0

## N_001
No	Task:	CSL Language :: Concat & Replication			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			MH	05/12/2008	05/17/2008		80
		Examples			MH,AH	05/07/2008	05/10/2008		100
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/06/2008		100
			Treewalker		AB	05/05/2008	05/06/2008		100
			CSLOM CMD		MP	05/08/2008	05/08/2008		80
			CSLOM		OS	05/07/2008	05/08/2008		100
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/05/2008	05/10/2008		100
			Adapter		MP	05/05/2008	05/08/2008		90
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser		N/A				100
			Treewalker		N/A				100
			CDOM		N/A				100
			CDOM checker		N/A				100
			CDOM Verilog gen		AB				100
3	Testing	Specifications			MH	05/05/2008	05/07/2008		100
		Generated tests			MH,AH	05/05/2008	05/10/2008		75
		Manual tests							N/A
		Regression	golden		AB				0
			new		AH				0
	Overall status								83.82

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/MonicaH_TL.ods'#Sheet1
Owner:	Monica Helgiu
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	Documentation :: Spec	80		Fix documentation	Med
CSL Language :: Concat & Replication	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	High
CSL Language :: Concat & Replication	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High
CSL Language :: Concat & Replication	Testing :: Generated	100		Provide generated tests for the current task EDIT: updated with all concat tests. Please update your status.	High
CSL Autorouter :: connect()	Documentation :: Examples	100		Write in a temporary doc connect spec provided by DP	High
CSL Language :: do_not_gen_rtl()	Documentation :: Spec	100		Fix documentation	Med
CSL Language :: do_not_gen_rtl()	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	Med
CSL Language :: do_not_gen_cpp()	Documentation :: Spec	100		Fix documentation	Med
CSL Language :: do_not_gen_cpp()	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	Med
CSL Interconnect :: f2a matrix	Documentation :: Specs	100		Interconnect f2a matrix with valid and invalid cases (spec and documentation: interconnect)	High+
CSL Language :: X and Z values spec	Documentation :: Specs	80		Provide specification for numbers with X and Z (use the verilog spec)	High+
CSL Autrouter :: connect()	Documentation :: Specs	50		Fix the presentation for connect methods and current examples	High+

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/AnamariaH_TL.ods'#Sheet1
Owner:	Anamaria Helgiu
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	High++
CSL Language :: Concat & Replication	Testing :: Generated	50		Provide generated tests for the current task	High	Moved task to MH
CSL Language :: Concat & Replication	Testing :: Regression :: new	0		Add all tests to csl new for checking	Med
CSL Language :: Parameters	Documentation :: Examples	0		Provide CSL and Verilog examples for documentation	High+
CSL Language :: do_not_gen_rtl()	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	Med
CSL Language :: do_not_gen_cpp()	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	Med

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/OctavS_TL.ods'#Sheet1
Owner:	Octavian Stolnicu
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: Lexer & Parser	100		Add support for concat and replication	High++
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM	100		Review concat and replication implementation	High++
CSL Language :: Prefix & Suffix	SW :: CSL :: Lexer & Parser	100		Add support for prefix & suffix	High
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM	100		Add support for prefix & suffix	High
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Lexer & Parser	100		Add support for do_not_gen_rtl()	Med
CSL Language :: do_not_gen_rtl()	SW :: CSL :: CSLOM	100		Add support for do_not_gen_rtl()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Lexer & Parser	100		Add support for do_not_gen_cpp()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM	100		Add support for do_not_gen_cpp()	Med
CSL Language :: Parameters	SW :: CSL :: Lexer & Parser	100		Add support for parameters	High+
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: Lexer & Parser	100		Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: Lexer & Parser	100		Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: Lexer & Parser	100		Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	0		Attend BZ's CSLOM training classes	High++
CSL Language :: set_clock()	SW :: CSL :: CSLOM	0	Documentation?	Add support for set_clock()	High
Support :: Distributed regression	SW :: Support	0		Please test and provide functionality for the distributed regression. The script path is: trunk/scripts/ssh_dist_regress.pl	High
CSL Autorouter :: connect() method	SW :: CSL :: Lexer & Parser	90		Add support for all connect methods as described in auto router document (Current connect variants sub-chapter: pages 14-16)	High++

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/AndreiB_TL.ods'#Sheet1
Owner:	Andrei Branzila
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: Treewalker	100		Add support for concat and replication	High++
CSL Language :: Concat & Replication	SW :: CSL :: Csim_gen	0		Add support for concat and replication	Low	Suspended
CSL Language :: Concat & Replication	Testing :: Regression :: golden	0		Add tests from new to golden after all components comply	Low
CSL Language :: Parameters	SW :: CSL :: Treewalker	90		Add support for parameters	High
CSL Language :: Parameters	SW :: CSL :: Csim_gen	0		Add support for parameters	Low	Suspended
CSL Language :: Prefix & Suffix	SW :: CSL :: Treewalker	100		Add support for prefix & suffix	High
CSL Language :: Prefix & Suffix	SW :: CSL :: Csim_gen	0		Add support for prefix & suffix	Low	Suspended
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Treewalker	100		Add support for do_not_gen_rtl()	High
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: Treewalker	100		Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: Treewalker	100		Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: Treewalker	0		Add support for register_ios()	High
Predeclaration bug	All	100		Provide a solution for the predeclaration bug	High++
CSLOM training class	SW :: CSL :: CSLOM	50		Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0		Attend BZ's autorouter functionality presentation	High++
CSL Language :: support for concat in LHS	SW :: CSL :: Treewalker	100		Add support for concat in assignment LHS in Treewalker	High++
Memory Map specification	Documentation :: Spec	0		Provide specification for memory map with CGH	High++
ISA specification	Documentation :: Spec	0		Revise/Fix/Rewrite specification for ISA with CGH (check consistency between SW implementation and current documentation)	High++
CSL Autorouter :: connect() method	SW :: CSL :: Treewalker	100		Add support for all connect methods as described in auto router document (Current connect variants sub-chapter: pages 14-16)	High++

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/MihaelaP_TL.ods'#Sheet1
Owner:	Mihaela Plaesu
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM_cmd	80		Add support for concat and replication	High++
CSL Language :: Concat & Replication	SW :: CSL :: Adapter	90		Add support for concat and replication	High++	Needs some testing
CSL Language :: Parameters	SW :: CSL :: CSLOM_cmd	0	CSLOm support needed	Add support for parameters	High+
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM_cmd	90	CSLOm support needed	Add support for prefix & suffix	High
CSL Language :: Prefix & Suffix	SW :: CSL :: Adapter	30		Add support for prefix & suffix	High
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Adapter	0		Add support for do_not_gen_rtl()	High
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM_cmd	100	CSLOm support needed	Add support for do_not_gen_cpp()	High
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM_cmd	100	CSLOm support needed	Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: CSLOM_cmd	80	CSLOm support needed	Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: CSLOM_cmd	50	CSLOm/TW support needed	Add support for register_ios()	High
CSL Language :: register_ios()	SW :: CSL :: Adapter	0		Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	100		Attend BZ's CSLOM training classes	High++
Adapter prefix bug (duplicate port bug)	SW :: CSL :: Adapter	100		Fix Adapter duplicate port bug	High++	The test passes. Maybe some other test cases need to be checked.
CSL Language :: do_not_gen_rtl()	SW :: CSL :: CSLOM_cmd	100		Add support for do_not_gen_rtl()	High

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/AndreiS_TL.ods'#Sheet1
Owner:	Andrei Susnea
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for concat and replication	High++	Also added getWidth for concat and replication in CSLOM | 80% because it needs testing
CSL Language :: Parameters	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for parameters	High+
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for prefix & suffix	High
CSL Language :: do_not_gen_rtl()	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for do_not_gen_rtl()	High	N/A
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for do_not_gen_cpp()	High	N/A
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM check	100	CSLOM-	Add support for do_not_gen_cpp()	High	N/A
CSL Language :: set_clock()	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: CSLOM check	0	CSLOM-	Add support for set_clock()	High
CSLOM training class	SW :: CSL :: CSLOM	100		Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0		Attend BZ's autorouter functionality presentation	High++
CSL Language :: support for concat in LHS	SW :: CSL :: CSLOM	100		Add support for concat in assignment LHS in CSLOM and CSLOM checker	High++	Also added getWidth for ExprOp
support for X and Z in numbers	SW :: CSL :: CSLOM	0		Add support numbers with X and Z bit values. The spec should be the Verilog standard and MH will add this to CSL Language document	High++

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/PetronelaE_TL.ods'#Sheet1
Owner:	Petronela Ezaru
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: XML Gen	0		Add support for concat and replication	Low	Suspended
CSL Language :: Concat & Replication	SW :: CSL :: PDF Gen	0		Add support for concat and replication	Low	Suspended
CSL Language :: Parameters	SW :: CSL :: XML Gen	0		Add support for parameters	Low	Suspended
CSL Language :: Parameters	SW :: CSL :: PDF Gen	0		Add support for parameters	Low	Suspended
CSL Language :: Prefix & Suffix	SW :: CSL :: XML Gen	0		Add support for prefix & suffix	Low	Suspended
CSL Language :: Prefix & Suffix	SW :: CSL :: PDF Gen	0		Add support for prefix & suffix	Low	Suspended
CSL Language :: Parameters	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Parameters	Testing :: Generated	100		Provide generated tests for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: Prefix & Suffix	Testing :: Generated	20		Provide generated tests for the current task	High++
CSL Language :: set_clock()	Testing :: Specifications	0		Provide testing specifications (test matrix) for the current task	High++	Moved task to OB
CSL Language :: set_clock()	Testing :: Generated	0		Provide generated tests for the current task	High++	Moved task to OB
CSL Language :: register_ios()	Testing :: Specifications	0		Provide testing specifications (test matrix) for the current task	High++	Moved task to OB
CSL Language :: register_ios()	Testing :: Generated	0		Provide generated tests for the current task	High++	Moved task to OB
CSL Autorouter :: connect()	Testing :: Specifications	0		Provide testing specifications (test matrix) for the current task	High+
CSL Autorouter :: connect()	Testing :: Generated	0		Provide generated tests for the current task	High+
SystemC codegen	SW :: SystemC :: generator	0		Read SystemC documentation and understand CSL vs SystemC implementations of interconnect	High
SystemC codegen	SW :: SystemC :: generator	0		Ensure and provide SystemC generator interconnect support	High
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Verilog define generator	100		Add support for do_not_gen_rtl() in the Verilog define generator	High+

## N_002
No	Task:	CSL Language :: Parameters			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			CC	05/12/2008	05/17/2008		90
		Examples			CC,AH	05/05/2008	05/08/2008		45
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS				100
			Treewalker		AB	05/05/2008	05/08/2008		90
			CSLOM CMD		MP	05/08/2008	05/08/2008		80
			CSLOM		EC	05/05/2008	05/08/2008		50
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/05/2008	05/10/2008		0
			Adapter		TH	05/05/2008	05/08/2008		0
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser		N/A				100
			Treewalker		N/A				100
			CDOM		N/A				100
			CDOM checker		N/A				100
			CDOM Verilog gen		AB				100
3	Testing	Specifications			PE	05/05/2008	05/10/2008		100
		Generated tests			PE	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								77

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_003
No	Task:	CSL Language :: Prefix & Suffix			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			CC	05/19/2008	05/24/2008		50
		Examples			CC,CGH	05/05/2008	05/10/2008		70
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/06/2008		100
			Treewalker		AB	05/05/2008	05/06/2008		100
			CSLOM CMD		MP	05/08/2008	05/08/2008		90
			CSLOM		OS	05/08/2008	05/10/2008		100
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/05/2008	05/10/2008		0
			Adapter		MP	05/12/2008	05/14/2008		30
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser		N/A				100
			Treewalker		N/A				100
			CDOM		N/A				100
			CDOM checker		N/A				100
			CDOM Verilog gen		AB				100
3	Testing	Specifications			PE	05/05/2008	05/10/2008		100
		Generated tests			PE	05/05/2008	05/10/2008		20
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								77.33

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/CostelC_TL.ods'#Sheet1
Owner:	Costel Coutun
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	Documentation :: Spec	90		Documentation readability	Low
CSL Language :: Parameters	Documentation :: Examples	90		Provide CSL and Verilog examples for documentation	Low	Can't provide verilog examples yet
CSL Autorouter :: connect()	Documentation :: Spec	80		Merge docs provided by OB, CGH and MH regarding autorouter functionality and fix current spec	High++
CSL Language :: Prefix & Suffix	Documentation :: Spec	50		Documentation readability	Low
CSL Language :: Prefix & Suffix	Documentation :: Examples	70		Provide CSL and Verilog examples for documentation	High	Can't provide verilog examples yet
CSL Language :: gen_unique_rtl_modules()	Documentation :: Spec	50		Documentation readability	Low
CSL Language :: gen_unique_rtl_modules()	Documentation :: Examples	100		Provide CSL and Verilog examples for documentation	High
CSL Language :: set_clock()	Documentation :: Spec	50		Documentation readability	Low
CSL Language :: set_clock()	Documentation :: Examples	50		Provide CSL and Verilog examples for documentation	High
CSL Language :: register_ios()	Documentation :: Spec	50		Documentation readability	Low
CSL Language :: register_ios()	Documentation :: Examples	0		Provide CSL and Verilog examples for documentation	High

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/EugenC_TL.ods'#Sheet1
Owner:	Eugen Croitoru
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	SW :: CSL :: CSLOM	50		Add support for parameters	High++
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM	0		Add support for gen_unique_rtl_modules()	None	Moved to TH assignments
CSL Language :: set_clock()	SW :: CSL :: CSLOM	0		Add support for set_clock()	None	Moved to OS assignments
CSL Language :: register_ios()	SW :: CSL :: CSLOM	0		Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	0		Attend BZ's CSLOM training classes	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0		Attend BZ's autorouter functionality presentation	High++

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/TiberiuH_TL.ods'#Sheet1
Owner:	Tiberiu Haret
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	SW :: CSL :: Adapter	0	CSLOM	Add support for parameters	High
CSL Language :: do_not_gen_rtl()	SW :: Main :: CLI	100		Add support for do_not_gen_rtl()	Med
CSL Language :: do_not_gen_cpp()	SW :: Main :: CLI	0	Specs	Add support for do_not_gen_cpp()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Adapter	100		Add support for do_not_gen_cpp()	High
CSL Language :: gen_unique_rtl_module()	SW :: CSL :: Adapter	100		Add support for gen_unique_rtl_module()	High
CSLOM training class	SW :: CSL :: CSLOM	100		Attend BZ's CSLOM training classes	High++
CSL Interconnect :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM	50	Specs	Add support for gen_unique_rtl_modules()	High+
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Adapter	100		Add support for do_not_gen_rtl()	High
CSLOM :: Visitor	SW :: CSL :: Adapter	100		Change traversal functions to inline functions	Med
CDOM :: VHDL code generator	SW :: CDOM :: VHDL codegenr	15		Implement a VHDL code generator for interconnect	High	still lots to learn about both Verilog and VHDL, so it's going to take me some time to implement this

## N_004
No	Task:	CSL Language :: do_not_gen_rtl()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			MH	05/12/2008	05/17/2008		100
		Examples			MH,AH	05/05/2008	05/10/2008		100
2	Software development	Main + CLI + GUI			TH	05/12/2008	05/17/2008		100
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS				100
			Treewalker		AB				100
			CSLOM CMD		MP	05/14/2008	05/15/2008		100
			CSLOM		OS	05/12/2008	05/14/2008		100
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		100
			Adapter		TH	05/14/2008	05/15/2008		100
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen	PE				100
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/05/2008	05/10/2008		100
		Generated tests			OB	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_005
No	Task:	CSL Language :: do_not_gen_cpp()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			MH	05/12/2008	05/17/2008		100
		Examples			MH,AH	05/05/2008	05/10/2008		100
2	Software development	Main + CLI + GUI			TH				0
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS				100
			Treewalker		AB				100
			CSLOM CMD		MP	05/14/2008	05/15/2008		100
			CSLOM		OS	05/12/2008	05/14/2008		100
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		100
			Adapter		TH	05/14/2008	05/15/2008		100
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/05/2008	05/10/2008		100
		Generated tests			OB	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								90.91

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_006
No	Task:	CSL Language :: gen_unique_rtl_modules()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			CC	05/19/2008	05/24/2008		50
		Examples			CC,CGH	05/05/2008	05/10/2008		50
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS				100
			Treewalker		AB				100
			CSLOM CMD		MP	05/14/2008	05/15/2008		100
			CSLOM		TH	05/14/2008	05/16/2008		50
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		100
			Adapter		TH	05/14/2008	05/15/2008		100
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/05/2008	05/10/2008		100
		Generated tests			OB	05/05/2008	05/10/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								85

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_007
No	Task:	CSL Language :: set_clock()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			CC	05/19/2008	05/24/2008		50
		Examples			CC,CGH	05/05/2008	05/10/2008		25
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/09/2008		100
			Treewalker		AB	05/05/2008	05/09/2008		100
			CSLOM CMD		MP	05/14/2008	05/15/2008		80
			CSLOM		OS	05/14/2008	05/16/2008		0
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		0
			Adapter						N/A
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/26/2008	05/31/2008		100
		Generated tests			OB	05/26/2008	05/31/2008		100
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								61.67

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_008
No	Task:	CSL Language :: register_ios()			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			CC	05/19/2008	05/24/2008		50
		Examples			CC,CGH	05/05/2008	05/10/2008		0
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/05/2008	05/09/2008		100
			Treewalker		AB	05/05/2008	05/09/2008		0
			CSLOM CMD		MP	05/14/2008	05/15/2008		50
			CSLOM		EC	05/12/2008	05/14/2008		0
			Instance Tree + autorouter						N/A
			CSLOM Design Checker		AS	05/12/2008	05/17/2008		0
			Adapter		MP	05/14/2008	05/16/2008		0
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB	05/26/2008	05/31/2008		30
		Generated tests			OB	05/26/2008	05/31/2008		0
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								23

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_009
No	Task:	CSL Autorouter :: connect() method			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			OB,CC,BZ,CGH	05/05/2008	05/08/2008		86
		Examples			MH,AH	05/08/2008	05/16/2008		100
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser		OS	05/22/2008	05/23/2008		90
			Treewalker		AB	05/23/2008	05/23/2008		100
			CSLOM CMD						N/A
			CSLOM						N/A
			Instance Tree + autorouter		BZ	05/08/2008	05/14/2008		0
			CSLOM Design Checker						N/A
			Adapter						N/A
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications			OB,PE	05/12/2008	05/17/2008		35
		Generated tests			OB,PE	05/12/2008	05/17/2008		30
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								63

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/BogdanZ_TL.ods'#Sheet1
Owner:	Bogdan Zamfir
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM	100		Implement concat and replication + train OS/EC	High++	Has been implemented in cslom a long time ago
CSL Autorouter :: connect()	Documentation :: Spec	100		Detail current autorouter functionality to CGH	High++	Emails have been sent a long time ago.
CSL Autorouter :: connect()	SW :: CSL :: Autorouter	0		Provide autorouter functionality as in the spec document	High++
CSLOM implementation support	SW :: CSL :: CSLOM	0		Provide support to OS/EC/TH/AS to implement their CSLOM related tasks	High++
Predeclaration bug	All	100		Provide a solution for the predeclaration bug	High++	Solution: Change 75% of parser, cslom, cmd, checker, AutoRouter, instance Tree.
CSLOM training class	SW :: CSL :: CSLOM	0		CSLOM training classes for the following employees: EC, OS, MP, AS, TH, AB (about 1-2 hours/day when at least 80% of the attendees are present at the office)	High++
Autoruter functionality class	SW :: CSL :: Autorouter	0		Hold autorouter functionality presentation for the following employees: AS, EC, AB (about 1 hour/day when at least 60% of the attendees are present at the office)	High++
Coverage tool recommandation	SW :: Support	100		Recommend in a report a coverage tool according to its performance and features (evaluation should contain both a commercial and a free candidate). After the report is compiled please send it to Dinesh and Derek	High++	lcov with a machine farm about 8 cores at least
Coverage tool evaluation	SW :: Support	0	Derek.	Evaluate Bullseye coverage tool	High++	I need Derek to send the evaluation product first
CSIM functionality	SW :: CSL :: CSIM	0		Need solutions and implementations for: single action compile, generated values difference between CSIM and Modelsim (due to flip flop propagation issue) talk to AB/OS for examples, load feature to load stimulus vectors from a file	High++

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/CristianH_TL.ods'#Sheet1
Owner:	Cristian Haba
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Autorouter :: connect()	Documentation :: Spec	50		Review and note in a temporary doc current autorouter functionality (provided by BZ)	High++
CSL Language :: Prefix & Suffix	Documentation :: Examples	70		Provide CSL and Verilog examples for documentation	High
CSL Language :: gen_unique_rtl_modules()	Documentation :: Examples	0		Provide CSL and Verilog examples for documentation	High
CSL Language :: set_clock()	Documentation :: Examples	0		Provide CSL and Verilog examples for documentation	High
CSL Language :: register_ios()	Documentation :: Examples	0		Provide CSL and Verilog examples for documentation	High
Memory Map specification	Documentation :: Spec	0		Provide specification for memory map with AB	High++
ISA specification	Documentation :: Spec	0		Revise/Fix/Rewrite specification for ISA with CGH (check consistency between SW implementation and current documentation)	High++

## 'file:///storage/users/andreib/svn/misc/project_management/archive/2008.05/users/OanaB_TL.ods'#Sheet1
Owner:	Oana Botez
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Autorouter :: connect()	Documentation :: Spec	100		Outline current functionality in a temporary doc for each method from the autorouter doc	High++
CSL Language :: do_not_gen_rtl()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High
CSL Language :: do_not_gen_rtl()	Testing :: Generated	100		Provide generated tests for the current task	High
CSL Language :: do_not_gen_cpp()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High
CSL Language :: do_not_gen_cpp()	Testing :: Generated	100		Provide generated tests for the current task	High
CSL Language :: gen_unique_rtl_modules()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High+
CSL Language :: gen_unique_rtl_modules()	Testing :: Generated	100		Provide generated tests for the current task	High+
CSL Autorouter :: connect()	Testing :: Specifications	70		Provide testing specifications (test matrix) for the current task	High+
CSL Autorouter :: connect()	Testing :: Generated	60		Provide generated tests for the current task	High+
CSL Language :: set_clock()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: set_clock()	Testing :: Generated	100		Provide generated tests for the current task	High++
CSL Language :: register_ios()	Testing :: Specifications	30		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: register_ios()	Testing :: Generated	0		Provide generated tests for the current task	High++
Auto CSL generation	SW :: Support	0		Cslc/misc/projects/csl_ifc_csv_gen / read the README / run the program / in the README file / fix the program / The program needs to do a bottom up traversal to put the top unit at the end of the file so that connect statements do not cause an error / The list of ifc's should be read in and compared to the ifc names in the spreadsheet. / The list of instances in the hier file should match the names in the left column and upper row. / The list of instances in the left column and the upper row need to have the same order.	High++

## N_010
No	Task:	CSLOM implementation support			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: CSLOM				BZ	05/05/2008	05/17/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_011
No	Task:	Predeclaration bug			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	All				BZ,AB	05/05/2008	05/07/2008		100		According to BZ's suggestion this is not C++ compatible (also this has been tested). I'll mark the issue solved for now and if necessary will return at a later date
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_012
No	Task:	CSLOM training class			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: CSLOM				BZ	05/07/2008			50		No end date
	Overall status								50

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_013
No	Task:	Autoruter functionality class			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: Autorouter				BZ	05/07/2008			0		No end date
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_014
No	Task:	CSLOM implementation support			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: CSLOM				BZ	05/07/2008			0		No end date
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_015
No	Task:	Adapter prefix bug (duplicate port bug)			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL ::Adapter				MP	05/07/2008	05/09/2008		100
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_016
No	Task:	SystemC codegen			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: SystemC :: generator				PE	05/12/2008	05/30/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_017
No	Task:	Interconnect F2A valid/invalid cases matrix			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation :: Specs				MH	05/14/2008	05/16/2008		100
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_018
No	Task:	Support for concat in assignment LHS			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL Flow				AS, AB	05/14/2008	05/15/2008		100
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_019
No	Task:	CSLOm Visitor traversal functions update			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	CSLOM:: Visitor				TH	05/15/2008	05/15/2008		100
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_020
No	Task:	Coverage tool recommandation			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: Support				BZ	05/16/2008	05/20/2008		100
	Overall status								100

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_021
No	Task:	VHDL Code generator			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: VHDL				TH	05/22/2008	06/07/2008		15
	Overall status								15

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_022
No	Task:	Distributed regression			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: Support				OS	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_023
No	Task:	CSIM functionality			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: CSL :: CSIM				BZ	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_024
No	Task:	Coverage tool evaluation			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: Support				BZ	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_025
No	Task:	CSL Language :: Support for X and Z in numbers			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation	Spec			MH	05/22/2008	05/26/2008		80
		Examples							N/A
2	Software development	Main + CLI + GUI							N/A
		CSL Flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CSLOM CMD						N/A
			CSLOM		AS	05/22/2008	05/31/2008		0
			Instance Tree + autorouter						N/A
			CSLOM Design Checker						N/A
			Adapter						N/A
			CSIM	CSIM lib					N/A
				CSIM gen					N/A
			Generators	CPP gen					N/A
				Verilog define gen					N/A
				XML gen					N/A
				PDF gen					N/A
		Verilog flow	Preprocessor						N/A
			Lexer + Parser						N/A
			Treewalker						N/A
			CDOM						N/A
			CDOM checker						N/A
			CDOM Verilog gen						N/A
3	Testing	Specifications							N/A
		Generated tests							N/A
		Manual tests							N/A
		Regression	golden						N/A
			new						N/A
	Overall status								40

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_026
No	Task:	Memory Map specification			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation :: Spec				CGH, AB	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_027
No	Task:	ISA specification			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	Documentation :: Spec				CGH, AB	05/22/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet

## N_028
No	Task:	Auto CSL generation			owner	start date	end date	delay	status	show stoppers	Obs	Task details
	Component Name
1	SW :: Support				OB	05/26/2008	05/31/2008		0
	Overall status								0

	conventions
	filename:	YYYY_MM_TL.ods
	for each task:	new sheet
	unfinished taks:	add to the next month
	sheet name:	N_xxx/D_xxx	Not done/Done / xxx – number	always move D_Taskname to the end
	status colors:	red 0% / yellow 1-65% / violet 66-99% / green 100% / magenta NA	see style & formatting
	TaskMap:	at the beginning of each file
		contains: TaskID, Real task name, link to task sheet