## Sheet1
Owner:	Oana Botez
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Autorouter :: connect()	Documentation :: Spec	100		Outline current functionality in a temporary doc for each method from the autorouter doc	High++
CSL Language :: do_not_gen_rtl()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High
CSL Language :: do_not_gen_rtl()	Testing :: Generated	100		Provide generated tests for the current task	High
CSL Language :: do_not_gen_cpp()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High
CSL Language :: do_not_gen_cpp()	Testing :: Generated	100		Provide generated tests for the current task	High
CSL Language :: gen_unique_rtl_modules()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High+
CSL Language :: gen_unique_rtl_modules()	Testing :: Generated	100		Provide generated tests for the current task	High+
CSL Autorouter :: connect()	Testing :: Specifications	70		Provide testing specifications (test matrix) for the current task	High+
CSL Autorouter :: connect()	Testing :: Generated	60		Provide generated tests for the current task	High+
CSL Language :: set_clock()	Testing :: Specifications	100		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: set_clock()	Testing :: Generated	100		Provide generated tests for the current task	High++
CSL Language :: register_ios()	Testing :: Specifications	30		Provide testing specifications (test matrix) for the current task	High++
CSL Language :: register_ios()	Testing :: Generated	0		Provide generated tests for the current task	High++
Auto CSL generation	SW :: Support	0		Cslc/misc/projects/csl_ifc_csv_gen / read the README / run the program / in the README file / fix the program / The program needs to do a bottom up traversal to put the top unit at the end of the file so that connect statements do not cause an error / The list of ifc's should be read in and compared to the ifc names in the spreadsheet. / The list of instances in the hier file should match the names in the left column and upper row. / The list of instances in the left column and the upper row need to have the same order.	High++