## Sheet1
Owner:	Octavian Stolnicu
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	SW :: CSL :: Lexer & Parser	100		Add support for concat and replication	High++
CSL Language :: Concat & Replication	SW :: CSL :: CSLOM	100		Review concat and replication implementation	High++
CSL Language :: Prefix & Suffix	SW :: CSL :: Lexer & Parser	100		Add support for prefix & suffix	High
CSL Language :: Prefix & Suffix	SW :: CSL :: CSLOM	100		Add support for prefix & suffix	High
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Lexer & Parser	100		Add support for do_not_gen_rtl()	Med
CSL Language :: do_not_gen_rtl()	SW :: CSL :: CSLOM	100		Add support for do_not_gen_rtl()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Lexer & Parser	100		Add support for do_not_gen_cpp()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: CSLOM	100		Add support for do_not_gen_cpp()	Med
CSL Language :: Parameters	SW :: CSL :: Lexer & Parser	100		Add support for parameters	High+
CSL Language :: gen_unique_rtl_modules()	SW :: CSL :: Lexer & Parser	100		Add support for gen_unique_rtl_modules()	High
CSL Language :: set_clock()	SW :: CSL :: Lexer & Parser	100		Add support for set_clock()	High
CSL Language :: register_ios()	SW :: CSL :: Lexer & Parser	100		Add support for register_ios()	High
CSLOM training class	SW :: CSL :: CSLOM	0		Attend BZ's CSLOM training classes	High++
CSL Language :: set_clock()	SW :: CSL :: CSLOM	0	Documentation?	Add support for set_clock()	High
Support :: Distributed regression	SW :: Support	0		Please test and provide functionality for the distributed regression. The script path is: trunk/scripts/ssh_dist_regress.pl	High
CSL Autorouter :: connect() method	SW :: CSL :: Lexer & Parser	90		Add support for all connect methods as described in auto router document (Current connect variants sub-chapter: pages 14-16)	High++