## Sheet1
Owner:	Tiberiu Haret
Task	Component	Status	Show Stopper	Description	Priority	Obs
CSL Language :: Parameters	SW :: CSL :: Adapter	0	CSLOM	Add support for parameters	High
CSL Language :: do_not_gen_rtl()	SW :: Main :: CLI	100		Add support for do_not_gen_rtl()	Med
CSL Language :: do_not_gen_cpp()	SW :: Main :: CLI	0	Specs	Add support for do_not_gen_cpp()	Med
CSL Language :: do_not_gen_cpp()	SW :: CSL :: Adapter	100		Add support for do_not_gen_cpp()	High
CSL Language :: gen_unique_rtl_module()	SW :: CSL :: Adapter	100		Add support for gen_unique_rtl_module()	High
CSLOM training class	SW :: CSL :: CSLOM	100		Attend BZ's CSLOM training classes	High++
CSL Interconnect :: gen_unique_rtl_modules()	SW :: CSL :: CSLOM	50	Specs	Add support for gen_unique_rtl_modules()	High+
CSL Language :: do_not_gen_rtl()	SW :: CSL :: Adapter	100		Add support for do_not_gen_rtl()	High
CSLOM :: Visitor	SW :: CSL :: Adapter	100		Change traversal functions to inline functions	Med
CDOM :: VHDL code generator	SW :: CDOM :: VHDL codegenr	15		Implement a VHDL code generator for interconnect	High	still lots to learn about both Verilog and VHDL, so it's going to take me some time to implement this