## Sheet1
Owner:	Monica Helgiu
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Language :: Concat & Replication	Documentation :: Spec	100				Fix documentation	Med
CSL Language :: Concat & Replication	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	High
CSL Language :: Concat & Replication	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High
CSL Language :: Concat & Replication	Testing :: Generated	100				Provide generated tests for the current task EDIT: updated with all concat tests. Please update your status.	High
CSL Autorouter :: connect()	Documentation :: Examples	100				Write in a temporary doc connect spec provided by DP	High
CSL Language :: do_not_gen_cpp()	Documentation :: Spec	100				Fix documentation	Med
CSL Language :: do_not_gen_cpp()	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	Med
CSL Language :: X and Z values spec	Documentation :: Specs	80				Provide specification for numbers with X and Z (use the verilog spec)	High+
CSL Autrouter :: connect()	Documentation :: Specs	100				Fix the presentation for connect methods and current examples	High+
CSL Language :: Parameters	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	Low
CSL Language :: Prefix & Suffix	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	High
CSL Language :: gen_unique_rtl_modules()	Documentation :: Examples	100				Provide CSL and Verilog examples for documentation	High
CSL Language :: set_clock()	Documentation :: Examples	90				Provide CSL and Verilog examples for documentation	High
CSL Language :: register_ios()	Documentation :: Examples	90				Provide CSL and Verilog examples for documentation	High
CSL Autrouter :: connect()	Documentation :: Specs	90				Update connect methods naming (connect_by_name + connect_units)	High+
Docs :: CSL Language	Documentation :: Spec	90				Add Derek's markups to document	High++