## Sheet1
Owner:	Oana Botez
Task	Component	Status	Start date	End date	Show Stopper	Description	Priority	Obs
CSL Autorouter :: connect()	Documentation :: Spec	100				Outline current functionality in a temporary doc for each method from the autorouter doc	High++
CSL Language :: do_not_gen_cpp()	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High
CSL Language :: do_not_gen_cpp()	Testing :: Generated	100				Provide generated tests for the current task	High
CSL Language :: gen_unique_rtl_modules()	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High+
CSL Language :: gen_unique_rtl_modules()	Testing :: Generated	100				Provide generated tests for the current task	High+
CSL Autorouter :: connect()	Testing :: Specifications	100	12/06/2008	13/06/2008		Provide testing specifications (test matrix) for the current task	High+
CSL Autorouter :: connect()	Testing :: Generated	100	13/06/2008	05/07/2008		Provide generated tests for the current task	High+
CSL Language :: set_clock()	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High++
CSL Language :: set_clock()	Testing :: Generated	100				Provide generated tests for the current task	High++
CSL Language :: register_ios()	Testing :: Specifications	100				Provide testing specifications (test matrix) for the current task	High++
CSL Language :: register_ios()	Testing :: Generated	100	02/06/2008	09/06/2008		Provide generated tests for the current task	High++
Auto CSL generation	SW :: Support	0				Cslc/misc/projects/csl_ifc_csv_gen / read the README / run the program / in the README file / fix the program / The program needs to do a bottom up traversal to put the top unit at the end of the file so that connect statements do not cause an error / The list of ifc's should be read in and compared to the ifc names in the spreadsheet. / The list of instances in the hier file should match the names in the left column and upper row. / The list of instances in the left column and the upper row need to have the same order.	Low
CSL Language :: Parameters	Documentation :: Spec	90				Documentation readability	Low
CSL Language :: Prefix & Suffix	Documentation :: Spec	50				Documentation readability	Low
CSL Language :: gen_unique_rtl_modules()	Documentation :: Spec	50				Documentation readability	Low
CSL Language :: set_clock()	Documentation :: Spec	100				Documentation readability	Low
CSL Language :: register_ios()	Documentation :: Spec	70				Documentation readability	Low
Docs :: CSL Isa	Documentation :: Spec	100	09/06/2208	12/06/2008		Add Derek's markups to document	High++